## EARLY CASE
Activity Status | (*)WBS Name | Activity Name | (*)Start | (*)Finish | Original Duration(h) | GWDXAG-Asset | GWDXAG-Rig Name | GWDXAG-Region | GWDXAG-Well Type | GWDXAG-Rig Activity Type | GWDXAG-Estimate
Completed | Early Case | Rig Intake and Start up | 2025-03-03 | 2025-04-02 | 12 | GOM.Region | EXP.Transocean Invictus | GOM | X | RSU | Early
Completed | Early Case | GC868-2 MD611 (SWX7) TOP HOLE DRL | 2025-04-02 | 2025-04-10 | 8 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Completed | Early Case | GC868-3 (SWX8) TOP HOLE DRL | 2025-04-10 | 2025-04-21 | 8 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Completed | Early Case | GC868-1 (SWX4) ST DRL | 2025-04-21 | 2025-05-29 | 34 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Completed | Early Case | GC868-1 (SWX4) CPL | 2025-05-29 | 2025-07-21 | 41 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Early
In Progress | Early Case | GC868-2 MD611 (SWX7) DRL | 2025-07-21 | 2025-09-06 | 47 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | GC868-2 MD611 (SWX7) CPL | 2025-09-06 | 2025-10-13 | 37 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Early
Not Started | Early Case | GC868-3 (SWX8) DRL | 2025-10-13 | 2025-11-24 | 42 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | GC868-3 (SWX8) CPL | 2025-11-24 | 2026-01-10 | 47 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Early
Not Started | Early Case | WEST BUMP APPRAISAL DRL | 2026-01-10 | 2026-06-28 | 169 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida Batch Set (Paleogene) DRL | 2026-06-28 | 2026-08-21 | 54 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida (KA-112) (Paleogene) DRL | 2026-08-21 | 2026-11-20 | 91 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida (KA-114) (Paleogene) DRL | 2026-11-20 | 2027-02-20 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida (KA-111) (Paleogene) DRL | 2027-02-20 | 2027-05-23 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida (KA-214) (Paleogene) DRL | 2027-05-23 | 2027-08-23 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | Kaskida (KA-212) (Paleogene) DRL | 2027-08-23 | 2027-11-23 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | Kaskida (KA-211) (Paleogene) DRL | 2027-11-23 | 2028-02-23 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | Brazos DRL | 2028-02-23 | 2028-06-23 | 121 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Garibaldi DRL | 2028-06-23 | 2028-10-22 | 121 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | White Space | 2028-10-22 | 2030-05-01 | 556 | GOM.Region | EXP.Transocean Invictus | GOM | X | WS | Early
Not Started | Early Case | WEST BUMP 1 DRL | 2030-05-01 | 2030-09-28 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | White Space | 2030-09-28 | 2031-05-10 | 224 | GOM.Region | EXP.Transocean Invictus | GOM | X | WS | Early
Not Started | Early Case | WEST BUMP 2 DRL | 2031-05-10 | 2031-10-07 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Gila 1 DRL | 2031-10-07 | 2032-03-05 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Gila 2 DRL | 2032-03-05 | 2032-08-02 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Gila 3 DRL | 2032-08-02 | 2032-12-30 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Conifer 3 DRL | 2032-12-30 | 2033-05-29 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Conifer 4 DRL | 2033-05-29 | 2033-10-26 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | WEST BUMP 3 DRL | 2033-10-26 | 2033-12-25 | 60 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | White Space | 2033-12-25 | 2035-02-01 | 403 | GOM.Region | EXP.Transocean Invictus | GOM | X | WS | Early
Not Started | Early Case | Gibson 1 DRL | 2035-02-01 | 2035-07-01 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Gibson 2 DRL | 2035-07-01 | 2035-11-28 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Conifer 5 DRL | 2035-11-28 | 2036-04-26 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | West Bump 4 DRL | 2036-04-26 | 2036-09-23 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | RIG INTAKE | 2028-01-20 | 2028-02-29 | 40 | GOM.Kaskida | GOM.Atlas | GOM | X | RSU | Early
Not Started | Early Case | Kaskida (KA-112) (Paleogene) CPL | 2028-02-29 | 2028-04-27 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-114) (Paleogene) CPL | 2028-04-27 | 2028-06-24 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-111) (Paleogene) CPL | 2028-06-24 | 2028-08-21 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-214) (Paleogene) CPL | 2028-08-21 | 2028-10-18 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-212) (Paleogene) CPL | 2028-10-18 | 2028-12-15 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-211) (Paleogene) CPL | 2028-12-15 | 2029-02-11 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-212) (Paleogene) CPL | 2029-02-11 | 2029-03-23 | 40 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-211) (Paleogene) CPL | 2029-03-23 | 2029-05-02 | 40 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-111) (Paleogene) CPL | 2029-05-02 | 2029-06-11 | 40 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-113) (Paleogene) CPL | 2029-06-11 | 2029-07-21 | 40 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | KC010 - Guadalupe 1 (Paleogene) CPL | 2029-07-21 | 2029-09-04 | 45 | GOM.Kaskida | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | KC010 - Guadalupe 2 (Paleogene) CPL | 2029-09-04 | 2029-10-19 | 45 | GOM.Kaskida | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2029-10-19 | 2029-11-13 | 25 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Tiber (TI-213) (Paleogene) CPL | 2029-11-13 | 2029-12-23 | 40 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-214) (Paleogene) CPL | 2029-12-23 | 2030-02-01 | 40 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | White Space | 2030-02-01 | 2030-10-01 | 242 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | West Bump 1 CPL | 2030-10-01 | 2030-11-30 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2030-11-30 | 2031-10-07 | 311 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | West Bump 2 CPL | 2031-10-07 | 2031-12-06 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2031-12-06 | 2032-07-01 | 208 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Conifer 1 CPL | 2032-07-01 | 2032-08-30 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Conifer 2 CPL | 2032-08-30 | 2032-10-29 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2032-10-29 | 2033-01-02 | 65 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Gila 1 CPL | 2033-01-02 | 2033-03-03 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Gila 2 CPL | 2033-03-03 | 2033-05-02 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Gila 3 CPL | 2033-05-02 | 2033-07-01 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2033-07-01 | 2033-10-28 | 119 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | West Bump 3 CPL | 2033-10-28 | 2033-12-27 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Conifer 3 CPL | 2033-12-27 | 2034-02-25 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Conifer 4 CPL | 2034-02-25 | 2034-04-26 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2034-04-26 | 2035-11-28 | 581 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Gibson 1 CPL | 2035-11-28 | 2036-01-27 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Gibson 2 CPL | 2036-01-27 | 2036-03-27 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2036-03-27 | 2036-04-30 | 34 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Conifer 5 CPL | 2036-04-30 | 2036-06-29 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2036-06-29 | 2036-09-28 | 91 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | West Bump 4 CPL | 2036-09-28 | 2036-11-27 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Completed | Early Case | STUP | 2022-01-25 | 2022-03-03 | 27 | GOM.Region | GOM.Auriga | GOM | OTH | RM | Early
Completed | Early Case | ATL 802 DRL | 2022-03-03 | 2022-04-26 | 37 | GOM.Atlantis | GOM.Auriga | GOM | DVP | DRL | Early
Completed | Early Case | DC222 (nB54 ) DRL | 2022-04-26 | 2022-09-05 | 30 | GOM.Atlantis | GOM.Auriga | GOM | DVP | DRL | Early
Completed | Early Case | DC214 (H75) BWM | 2022-09-05 | 2022-09-06 | 2 | GOM.Atlantis | GOM.Auriga | GOM | X | RM | Early
Completed | Early Case | DC214 (H75) DRL | 2022-09-06 | 2022-10-23 | 23 | GOM.Atlantis | GOM.Auriga | GOM | DVP | DRL | Early
Completed | Early Case | DC214 (H75) CPL | 2022-10-23 | 2022-11-28 | 35 | GOM.Atlantis | GOM.Auriga | GOM | DVP | CPL | Early
Completed | Early Case | ATL 802 CPL | 2022-11-28 | 2023-01-22 | 38 | GOM.Atlantis | GOM.Auriga | GOM | DVP | CPL | Early
Completed | Early Case | BWM | 2023-01-22 | 2023-01-26 | 5 | GOM.Atlantis | GOM.Auriga | GOM | X | RM | Early
Completed | Early Case | DC228 Open Water Work | 2023-01-26 | 2023-02-07 | 4 | GOM.Region | GOM.Auriga | GOM | DVP | WWS | Early
Completed | Early Case | BWM FMEA & UWILD | 2023-02-07 | 2023-02-20 | 7 | GOM.Atlantis | GOM.Auriga | GOM | X | RM | Early
Completed | Early Case | DC224 P&A | 2023-02-20 | 2023-03-05 | 14 | GOM.Atlantis | GOM.Auriga | GOM | DVP | P&A | Early
Completed | Early Case | DC228 (I54) ST DRL | 2023-03-05 | 2023-04-12 | 23 | GOM.Atlantis | GOM.Auriga | GOM | DVP | DRL | Early
Completed | Early Case | DC228 (I54) CPL | 2023-04-12 | 2023-06-02 | 35 | GOM.Atlantis | GOM.Auriga | GOM | DVP | CPL | Early
Completed | Early Case | BWM change out the choke and kill manifold | 2023-06-02 | 2023-06-12 | 10 | GOM.Atlantis | GOM.Auriga | GOM | X | RM | Early
Completed | Early Case | DC222 (nB54 )CPL | 2023-06-12 | 2023-09-27 | 35 | GOM.Atlantis | GOM.Auriga | GOM | DVP | CPL | Early
Completed | Early Case | BWM | 2023-09-27 | 2023-10-02 | 5 | GOM.Atlantis | GOM.Auriga | GOM | X | RM | Early
Completed | Early Case | DC215 (KG7) DRL | 2023-10-02 | 2024-01-05 | 38 | GOM.Atlantis | GOM.Auriga | GOM | DVP | DRL | Early
Completed | Early Case | DC215 (KG7) CPL | 2024-01-05 | 2024-02-13 | 35 | GOM.Atlantis | GOM.Auriga | GOM | DVP | CPL | Early
Completed | Early Case | Demob | 2024-02-13 | 2024-02-20 | 7 | GOM.Region | GOM.Auriga | GOM | X | MOB | Early
Completed | Early Case | Rig Start-Up | 2019-12-19 | 2020-02-11 | 20 | GOM.Region | GOM.Black Hornet | GOM | OTH | RM | Early
Completed | Early Case | MC822-13 SPc4 INTERV | 2020-02-11 | 2020-03-28 | 40 | GOM.Thunder Horse | GOM.Black Hornet | GOM | WW | WWI | Early
Completed | Early Case | MC520-4 (Manuel 2) CPL | 2020-03-28 | 2020-05-06 | 30 | GOM.Nakika | GOM.Black Hornet | GOM | EXP | CPL | Early
Completed | Early Case | BWM | 2020-05-06 | 2020-05-10 | 4 | GOM.GOMX | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC518-1 (Galapagos) DRL | 2020-05-10 | 2020-06-10 | 56 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | MC518-2 (Galapagos2) DRL | 2020-06-09 | 2020-11-13 | 59 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | THSX Batch 2 (8 Wells) DRL | 2020-11-13 | 2021-01-05 | 40 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | DRL | Early
Completed | Early Case | BWM Thruster repair on the Black Hornet | 2021-01-05 | 2021-01-22 | 10 | GOM.Region | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | BWM Puma West | 2021-01-22 | 2021-01-24 | 2 | GOM.Region | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | PUMA WEST DRL ST | 2021-01-24 | 2021-04-03 | 41 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | MC822-17 (SB7) BWM | 2021-04-03 | 2021-04-13 | 7 | GOM.Thunder Horse | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC822-17 (SB7) DRL | 2021-04-13 | 2021-06-23 | 69 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | DRL | Early
Completed | Early Case | MC822-17 (SB7) CPL | 2021-06-23 | 2021-07-17 | 30 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | CPL | Early
Completed | Early Case | MC776-6 INTERV BWM | 2021-07-17 | 2021-07-21 | 4 | GOM.Thunder Horse | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC776-6 (XP1) INTERV | 2021-07-21 | 2021-08-09 | 31 | GOM.Thunder Horse | GOM.Black Hornet | GOM | WW | WWP | Early
Completed | Early Case | MD GC826-5 P&A | 2021-08-09 | 2021-09-08 | 14 | GOM.Mad Dog | GOM.Black Hornet | GOM | OTH | P&A | Early
Completed | Early Case | MD GC826-4 P&A | 2021-09-08 | 2021-09-24 | 20 | GOM.Mad Dog | GOM.Black Hornet | GOM | OTH | P&A | Early
Completed | Early Case | TH MC776-1 P&A | 2021-09-24 | 2021-09-27 | 3 | GOM.Thunder Horse | GOM.Black Hornet | GOM | OTH | P&A | Early
Completed | Early Case | MC776-6 (XP1) INTERV | 2021-09-27 | 2021-11-01 | 26 | GOM.Thunder Horse | GOM.Black Hornet | GOM | WW | WWP | Early
Completed | Early Case | MC822-18 BWM | 2021-11-01 | 2021-11-03 | 2 | GOM.Thunder Horse | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC822-18 DRL | 2021-11-03 | 2022-01-13 | 69 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | DRL | Early
Completed | Early Case | MC822-18 CPL | 2022-01-13 | 2022-02-12 | 25 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | CPL | Early
Completed | Early Case | MC822-22 BWM | 2022-02-12 | 2022-02-18 | 2 | GOM.Thunder Horse | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC822-22 DRL | 2022-02-18 | 2022-06-25 | 68 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | DRL | Early
Completed | Early Case | MC822-22 CPL | 2022-06-25 | 2022-07-25 | 25 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | CPL | Early
Completed | Early Case | MC562-3 (ISABELA-3) BWM | 2022-07-25 | 2022-07-27 | 2 | GOM.Nakika | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC562-3 (ISABELA-3) DRL ST | 2022-07-27 | 2022-09-17 | 29 | GOM.Nakika | GOM.Black Hornet | GOM | MPP | DRL | Early
Completed | Early Case | GC821-3 (Puma West 2) BWM | 2022-09-17 | 2022-09-29 | 10 | GOM.GOMX | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | GC821-3 (Puma West 2) DRL | 2022-09-29 | 2023-01-30 | 68 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | GC777-1 PXA BWM | 2023-01-30 | 2023-02-03 | 4 | GOM.Thunder Horse | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | GC777-1 PXA INTERV | 2023-02-03 | 2023-02-26 | 22 | GOM.Thunder Horse | GOM.Black Hornet | GOM | WW | P&A | Early
Completed | Early Case | BWM | 2023-02-26 | 2023-03-02 | 7 | GOM.Nakika | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC520-6 Herschel-8 DRL | 2023-03-02 | 2023-06-28 | 42 | GOM.Nakika | GOM.Black Hornet | GOM | MPP | DRL | Early
Completed | Early Case | MC520-6 Herschel-8 CPL | 2023-06-28 | 2023-07-28 | 29 | GOM.Nakika | GOM.Black Hornet | GOM | MPP | CPL | Early
Completed | Early Case | BWM | 2023-07-28 | 2023-08-02 | 5 | GOM.Thunder Horse | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC822-11 (SB8) INTERV | 2023-08-02 | 2023-09-15 | 37 | GOM.Thunder Horse | GOM.Black Hornet | GOM | WW | WWP | Early
Completed | Early Case | MC777-10 (NPi15) BWM | 2023-09-15 | 2023-09-19 | 2 | GOM.Thunder Horse | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC777-10 (NPi15) DRL | 2023-09-19 | 2023-12-27 | 45 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | DRL | Early
Completed | Early Case | MC777-10 (NPi15) CPL | 2023-12-27 | 2024-02-14 | 29 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | CPL | Early
Completed | Early Case | Keltic S BWM | 2024-02-14 | 2024-02-20 | 4 | GOM.GOMX | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | Keltic S DRL | 2024-02-20 | 2024-05-17 | 66 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | BWM 5 Year BOP Recert | 2024-05-17 | 2024-05-24 | 10 | GOM.Region | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC822-1 PA | 2024-05-24 | 2024-07-01 | 50 | GOM.Thunder Horse | GOM.Black Hornet | GOM | WW | P&A | Early
Completed | Early Case | BWM | 2024-07-01 | 2024-07-04 | 3 | GOM.Thunder Horse | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | MC776-2 PA INTERV | 2024-07-04 | 2024-07-17 | 14 | GOM.Thunder Horse | GOM.Black Hornet | GOM | WW | P&A | Early
Completed | Early Case | BWM | 2024-07-17 | 2024-07-20 | 3 | GOM.Argos | GOM.Black Hornet | GOM | X | RM | Early
Completed | Early Case | GC869-1 PA INTERV | 2024-07-20 | 2024-08-03 | 17 | GOM.Argos | GOM.Black Hornet | GOM | WW | P&A | Early
Completed | Early Case | GC821-2 Puma West 1 PA INTERV | 2024-08-03 | 2024-08-17 | 17 | GOM.Puma | GOM.Black Hornet | GOM | WW | P&A | Early
Completed | Early Case | MC776-4 PA | 2024-08-17 | 2024-09-14 | 14 | GOM.Thunder Horse | GOM.Black Hornet | GOM | WW | P&A | Early
Completed | Early Case | White Space | 2024-09-14 | 2024-11-01 | 48 | GOM.Region | GOM.Black Hornet | GOM | X | WS | Early
Completed | Early Case | FAR SOUTH DRL | 2024-11-01 | 2025-03-25 | 75 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | Penguin BWM | 2025-03-25 | 2025-03-27 | 2 | GOM.GOMX | GOM.Black Hornet | GOM | X | RM | Early
In Progress | Early Case | Penguin DRL | 2025-03-27 | 2025-08-07 | 98 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | ATL DC153 DRL | 2025-08-07 | 2025-08-15 | 8 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | DC104 WI CPL | 2025-08-15 | 2025-09-19 | 35 | GOM.Atlantis | GOM.Black Hornet | GOM | DVI | CPL | Early
Not Started | Early Case | ATL DC153 DRL | 2025-09-19 | 2025-11-12 | 54 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | ATL DC153 CPL | 2025-11-12 | 2025-12-17 | 35 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2025-12-17 | 2026-01-01 | 15 | GOM.Region | GOM.Black Hornet | GOM | X | WS | Early
Not Started | Early Case | BWM | 2026-01-01 | 2026-01-04 | 3 | GOM.Nakika | GOM.Black Hornet | GOM | X | RM | Early
Not Started | Early Case | Fourier F7 DRL | 2026-01-04 | 2026-02-04 | 31 | GOM.Nakika | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | Fourier F7 CPL | 2026-02-04 | 2026-03-04 | 28 | GOM.Nakika | GOM.Black Hornet | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2026-03-04 | 2026-04-01 | 28 | GOM.Region | GOM.Black Hornet | GOM | X | WS | Early
Not Started | Early Case | Conifer DRL | 2026-04-01 | 2026-07-31 | 121 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | NBr2 DRL | 2026-07-31 | 2026-11-18 | 110 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | DRL | Early
Not Started | Early Case | NBr2 CPL | 2026-11-18 | 2027-01-02 | 45 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | CPL | Early
Not Started | Early Case | Mazama DRL | 2027-01-02 | 2027-04-09 | 97 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | RAPID CREEK DRL | 2027-04-09 | 2027-08-21 | 134 | GOM.GOMX | GOM.Black Hornet | GOM | MPP | DRL | Early
Not Started | Early Case | Duchess DRL | 2027-08-21 | 2027-11-19 | 90 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | TIBER (T1-212) (Paleogene) DRL | 2027-11-19 | 2028-02-21 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-211) (Paleogene) DRL | 2028-02-21 | 2028-05-25 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-111) (Paleogene) DRL | 2028-05-25 | 2028-08-27 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-113) (Paleogene) DRL | 2028-08-27 | 2028-11-29 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | KC010 - Guadalupe 1 (Paleogene) DRL | 2028-11-29 | 2029-03-13 | 104 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | KC010 - Guadalupe 2 (Paleogene) DRL | 2029-03-13 | 2029-06-25 | 104 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-213) (Paleogene) DRL | 2029-06-25 | 2029-09-27 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-214) (Paleogene) DRL | 2029-09-27 | 2029-12-30 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | Conifer 1 DRL | 2031-08-01 | 2031-12-29 | 150 | GOM.Paleogene | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | Conifer 2 DRL | 2031-12-29 | 2032-05-27 | 150 | GOM.Paleogene | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | Mob | 2020-07-15 | 2020-08-05 | 21 | GOM.Argos | GOM.Black Lion | GOM | X | MOB | Early
Completed | Early Case | WS | 2020-08-05 | 2020-09-08 | 27 | GOM.Argos | GOM.Black Lion | GOM | MPP | WS | Early
Completed | Early Case | GC824-1 (SWI4) TB | 2020-09-08 | 2020-10-06 | 14 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Completed | Early Case | GC824-1 (SWI4) CPL | 2020-10-06 | 2021-01-01 | 45 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | MPD BWM | 2021-01-01 | 2021-01-05 | 5 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC825-7 (SWP2) CPL | 2021-01-05 | 2021-02-10 | 32 | GOM.Argos | GOM.Black Lion | GOM | DVP | CPL | Early
Completed | Early Case | BWM SWP1 ST | 2021-02-10 | 2021-02-20 | 8 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC826-10 (SWP1) ST DRL | 2021-02-19 18:00 | 2021-04-26 | 24 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Completed | Early Case | BWM SWP1 C | 2021-04-26 | 2021-05-15 | 9 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC826-MD124 (SWP1) CPL | 2021-05-15 | 2021-06-16 | 30 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | BWM Isabela 3 | 2021-06-16 | 2021-06-28 | 5 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | MC562-3 (ISABELA-3) DRL | 2021-06-28 | 2021-10-26 | 71 | GOM.Nakika | GOM.Black Lion | GOM | MPP | DRL | Early
Completed | Early Case | MC520-5 (H5) CPL | 2021-10-26 | 2021-12-03 | 1 | GOM.Nakika | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | MC562-3 (ISABELA-3) CPL | 2021-12-03 | 2022-01-10 | 34 | GOM.Nakika | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC826-MD121 (SP15) BWM | 2022-01-10 | 2022-01-17 | 4 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC826-MD121 (SP15) DRL | 2022-01-17 | 2022-03-12 | 33 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Completed | Early Case | GC826-11 MD121 (SP15) CPL | 2022-03-12 | 2022-04-22 | 35 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC869-3 MD212 (SP7) BWM | 2022-04-22 | 2022-04-26 | 4 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC869-3 MD212 (SP7) CPL | 2022-04-26 | 2022-06-04 | 35 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC826-12 MD112 (SP1) BWM | 2022-06-04 | 2022-06-08 | 4 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC826-12 MD112 (SP1) DRL | 2022-06-08 | 2022-08-24 | 40 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Completed | Early Case | GC826-12 MD112 (SP1) CPL | 2022-08-24 | 2022-10-18 | 35 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | BWM | 2022-10-18 | 2022-10-25 | 7 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC825-3 MD414 (SWI1) CPL | 2022-10-25 | 2022-12-10 | 32 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC825-4 (SP10) MD223 Pull Upper Completion INTERV | 2022-12-10 | 2023-01-06 | 16 | GOM.Argos | GOM.Black Lion | GOM | WW | WWI | Early
Completed | Early Case | GC825-4 (SP10) MD223 UPPER CPL | 2023-01-06 | 2023-01-18 | 17 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC826-7 (SP12) MD214 Pull Upper Completion INTERV | 2023-01-18 | 2023-02-04 | 16 | GOM.Argos | GOM.Black Lion | GOM | WW | WWI | Early
Completed | Early Case | GC826-7 (SP12) MD214 UPPER CPL | 2023-02-04 | 2023-02-14 | 12 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC826-12 MD112 (SP1) UPPER CPL (26 days to POP) | 2023-02-14 | 2023-03-05 | 17 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC868-1 (SWX4) BWM | 2023-03-05 | 2023-03-08 | 3 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC868-1 (SWX4) DRL | 2023-03-08 | 2023-05-30 | 58 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2023-05-30 | 2023-06-06 | 7 | GOM.GOMX | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | Spinel DRL | 2023-06-06 | 2023-09-02 | 72 | GOM.GOMX | GOM.Black Lion | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2023-09-02 | 2023-09-05 | 3 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC824-1 MD413 (SWi4) Rig Injection Test | 2023-09-05 | 2023-10-06 | 16 | GOM.Argos | GOM.Black Lion | GOM | WW | WWS | Early
Completed | Early Case | GC825-3 MD414 (SWI1) CPL | 2023-10-06 | 2023-11-22 | 10 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC825-3 MD414 (SWI1) Rig Injection Test | 2023-11-22 | 2023-11-27 | 5 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC825-6 (SP5)MD213 CPL | 2023-11-27 | 2024-01-04 | 19 | GOM.Argos | GOM.Black Lion | GOM | DVP | CPL | Early
Completed | Early Case | GC826-9 MD511 (SI2) CPL | 2024-01-04 | 2024-02-29 | 38 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC826-9 MD511 (SI2) Rig Injection Test | 2024-02-29 | 2024-03-09 | 6 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | BWM Si4 | 2024-03-09 | 2024-03-13 | 5 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC869-2 MD421 (Si4) CPL | 2024-03-13 | 2024-04-27 | 35 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | GC869-2 MD421 (Si4) Rig Injection Test | 2024-04-27 | 2024-05-05 | 6 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | BWM MC562-3 (ISABELA-3) | 2024-05-05 | 2024-05-13 | 8 | GOM.Nakika | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | MC562-3 (ISABELA-3) ST2 DRL | 2024-05-13 | 2024-07-28 | 58 | GOM.Nakika | GOM.Black Lion | GOM | MPP | DRL | Early
Completed | Early Case | MC562-3 (ISABELA-3) CPL | 2024-07-28 | 2024-08-30 | 31 | GOM.Nakika | GOM.Black Lion | GOM | MPP | CPL | Early
Completed | Early Case | BWM 5yr bop recert | 2024-08-30 | 2024-09-14 | 12 | GOM.Argos | GOM.Black Lion | GOM | X | RM | Early
Completed | Early Case | GC825-MD424 (Si6) DRL | 2024-09-14 | 2025-02-05 | 45 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Completed | Early Case | GC825-MD424 (Si6) CPL | 2025-02-05 | 2025-05-11 | 49 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Completed | Early Case | BWM 5yr bop recert | 2025-05-11 | 2025-05-25 | 14 | GOM.Region | GOM.Black Lion | GOM | X | RM | Early
In Progress | Early Case | MD122 (SP3) DRL | 2025-05-25 | 2025-07-30 | 43 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | MD122 (SP3) CPL | 2025-07-30 | 2025-09-03 | 35 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | NPi22 DRL | 2025-09-03 | 2025-10-28 | 55 | GOM.Thunder Horse | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | NPi22 CPL | 2025-10-28 | 2025-12-14 | 47 | GOM.Thunder Horse | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | MD222 (SP4) DRL | 2025-12-14 | 2026-01-28 | 45 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | MD222 (SP4) CPL | 2026-01-28 | 2026-03-16 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Batch set MD411 / MD423 DRL | 2026-03-16 | 2026-03-24 | 8 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | MD423 DRL | 2026-03-24 | 2026-05-14 | 51 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | MD423 CPL | 2026-05-14 | 2026-06-28 | 45 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | MD411 (SI10) DRL | 2026-06-28 | 2026-08-26 | 59 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | MD411 (SI10) CPL | 2026-08-26 | 2026-10-07 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | Argos #14 SWP3 DRL | 2026-10-07 | 2026-12-09 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | MD Paleogene DRL | 2026-12-09 | 2026-12-31 | 22 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | Argos #14 SWP3 CPL | 2026-12-31 | 2027-02-16 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Si7 DRL | 2027-02-16 | 2027-04-20 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | Si7 CPL | 2027-04-20 | 2027-06-01 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | (SI9) DRL | 2027-06-01 | 2027-08-03 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | (SI9) CPL | 2027-08-03 | 2027-09-14 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | Argos SWX INFILL PH1 DRL | 2027-09-14 | 2027-11-03 | 50 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | Argos SWX INFILL PH1 CPL | 2027-11-03 | 2027-12-20 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Argos SWX INFILL PH2 DRL | 2027-12-20 | 2028-02-08 | 50 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | Argos SWX INFILL PH2 CPL | 2028-02-08 | 2028-03-26 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Argos INFILL 1 DRL | 2028-03-26 | 2028-05-28 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | Argos INFILL 1 CPL | 2028-05-28 | 2028-07-14 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Argos WI INFILL 1 DRL | 2028-07-14 | 2028-09-15 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | Argos WI INFILL 1 CPL | 2028-09-15 | 2028-10-27 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | Argos INFILL 2 DRL | 2028-10-27 | 2028-12-29 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | Argos INFILL 2 CPL | 2028-12-29 | 2029-02-14 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | MC383-4 Kepler 4 PA INTERV | 2029-02-14 | 2029-03-21 | 35 | GOM.Nakika | GOM.Black Lion | GOM | WW | P&A | Early
Not Started | Early Case | Kepler 2 (K-2) Zonal Isolation PA | 2029-03-21 | 2029-04-25 | 35 | GOM.Nakika | GOM.Black Lion | GOM | WW | P&A | Early
Not Started | Early Case | Manuel 1 (M-1) Zonal Isolation PA | 2029-04-25 | 2029-05-30 | 35 | GOM.Nakika | GOM.Black Lion | GOM | WW | P&A | Early
Not Started | Early Case | Fourier 2 (F-2) Zonal Isolation PA | 2029-05-30 | 2029-07-04 | 35 | GOM.Nakika | GOM.Black Lion | GOM | WW | P&A | Early
Not Started | Early Case | Argos WI INFILL 2 DRL | 2029-07-04 | 2029-09-05 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | Argos WI INFILL 2 CPL | 2029-09-05 | 2029-10-17 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | EXPLORATION PH 9 DRL | 2029-10-17 | 2030-01-15 | 90 | GOM.GOMX | GOM.Black Lion | GOM | EXP | DRL | Early
Completed | Early Case | Start up Canada | 2023-04-18 | 2023-05-05 | 15 | GOM.GOMX | GOM.Ice Max | CAN | EXP | MOB | Early
Completed | Early Case | Ephesus DRL | 2023-05-05 | 2023-06-30 | 92 | GOM.GOMX | GOM.Ice Max | CAN | EXP | DRL | Early
Completed | Early Case | Demob and transit to GoM | 2023-06-30 | 2023-07-18 | 30 | GOM.Region | GOM.Ice Max | GOM | X | RSU | Early
Completed | Early Case | RIG INTAKE | 2023-07-18 | 2023-09-21 | 45 | GOM.Region | GOM.Ice Max | GOM | X | RSU | Early
Completed | Early Case | MC822-19 (SB10) BWM | 2023-09-21 | 2023-09-23 | 2 | GOM.Thunder Horse | GOM.Ice Max | GOM | X | RM | Early
Completed | Early Case | MC822-19 (SB10) DRL | 2023-09-23 | 2024-04-09 | 80 | GOM.Thunder Horse | GOM.Ice Max | GOM | MPP | DRL | Early
Completed | Early Case | MC775-4 (NPi21) BWM | 2024-04-09 | 2024-04-16 | 7 | GOM.Thunder Horse | GOM.Ice Max | GOM | X | RM | Early
Completed | Early Case | MC775-4 (NPi21) DRL | 2024-04-16 | 2024-07-29 | 43 | GOM.Thunder Horse | GOM.Ice Max | GOM | DVP | DRL | Early
Completed | Early Case | MC775-4 (NPi21) CPL | 2024-07-29 | 2024-09-24 | 34 | GOM.Thunder Horse | GOM.Ice Max | GOM | DVP | CPL | Early
Completed | Early Case | DC103 PA | 2024-09-24 | 2024-12-15 | 55 | GOM.Atlantis | GOM.Ice Max | GOM | WW | P&A | Early
Completed | Early Case | DC112 INTERV | 2024-12-15 | 2025-01-01 | 17 | GOM.Atlantis | GOM.Ice Max | GOM | WW | WWP | Early
Completed | Early Case | DC123 Decomp PA | 2025-01-01 | 2025-02-08 | 24 | GOM.Atlantis | GOM.Ice Max | GOM | DVP | P&A | Early
Completed | Early Case | DC123 ST DRL | 2025-02-08 | 2025-04-18 | 12 | GOM.Atlantis | GOM.Ice Max | GOM | MPP | DRL | Early
Completed | Early Case | DC123 ST CPL | 2025-04-18 | 2025-05-24 | 23 | GOM.Atlantis | GOM.Ice Max | GOM | DVP | CPL | Early
In Progress | Early Case | DC104 WI DRL | 2025-05-24 | 2025-08-09 | 38 | GOM.Atlantis | GOM.Ice Max | GOM | DVI | DRL | Early
Not Started | Early Case | MC777-4 PA | 2025-08-09 | 2025-09-25 | 47 | GOM.Thunder Horse | GOM.Ice Max | GOM | WW | P&A | Early
Not Started | Early Case | White Space | 2025-09-25 | 2025-09-29 | 4 | GOM.Region | GOM.Ice Max | GOM | X | WS | Early
Not Started | Early Case | Demob | 2025-09-29 | 2025-10-06 | 7 | GOM.Region | GOM.Ice Max | GOM | X | MOB | Early
Completed | Early Case | STUP Pumping vessel | 2022-11-09 | 2023-02-12 | 53 | GOM.Region | GOM.LWI.ISLINTER | GOM | OTH | RM | Early
Completed | Early Case | DC317 (RLWI) INTERV | 2023-02-12 | 2023-04-03 | 11 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | DC121 (RLWI) BWM | 2023-04-03 | 2023-05-01 | 6 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | X | RM | Early
Completed | Early Case | DC121 (RLWI) INTERV | 2023-05-01 | 2023-05-08 | 12 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | DC123 (RLWI) BWM | 2023-05-08 | 2023-05-14 | 6 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | X | RM | Early
Completed | Early Case | DC123 Mars choke insert (RLWI) INTERV | 2023-05-14 | 2023-06-02 | 20 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | DC111 BWM (RLWI) INTERV | 2023-06-02 | 2023-06-09 | 4 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | X | RM | Early
Completed | Early Case | DC111 (RLWI) INTERV (19 days to Pop) | 2023-06-09 | 2023-06-23 | 33 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | DC132 (RLWI) BWM | 2023-06-23 | 2023-06-25 | 2 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | X | RM | Early
Completed | Early Case | DC132 (RLWI) INTERV | 2023-06-25 | 2023-07-18 | 20 | GOM.Atlantis | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | MC822-14 WSJI INTERV | 2023-07-18 | 2023-09-14 | 25 | GOM.Thunder Horse | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | Manuel 2 BWM | 2023-09-14 | 2023-09-25 | 6 | GOM.Nakika | GOM.LWI.ISLINTER | GOM | X | RM | Early
Completed | Early Case | Manuel 2 INTERV | 2023-09-25 | 2023-10-07 | 20 | GOM.Nakika | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | MC822-10 WSJI INTERV | 2023-10-07 | 2023-10-30 | 17 | GOM.Thunder Horse | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | MC566-F5 INTERV | 2023-10-30 | 2023-11-28 | 20 | GOM.Nakika | GOM.LWI.ISLINTER | GOM | WW | WWP | Early
Completed | Early Case | Woodside Farm out | 2023-11-28 | 2023-12-19 | 21 | GOM.Region | GOM.LWI.ISLINTER | GOM | X | RM | Early
Completed | Early Case | MC776-6 (RLWI) INTERV | 2019-08-16 | 2019-08-27 | 11 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW |  | Early
Completed | Early Case | MOB | 2020-01-19 | 2020-01-28 | 10 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | MOB | Early
Completed | Early Case | MC776-9 (NPi5w) (RLWI) INTERV Injection Log | 2020-01-28 | 2020-02-18 | 19 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW |  | Early
Completed | Early Case | MC776-5 (RLWI) INTERV | 2020-02-18 | 2020-03-16 | 16 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW |  | Early
Completed | Early Case | ISA-1 ISO Plug (RLWI) INTERV | 2020-03-16 | 2020-04-12 | 21 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | WW |  | Early
Completed | Early Case | MC776-7 (NPi2W) (RLWI) INTERV Injection Log | 2020-04-12 | 2020-05-14 | 30 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW |  | Early
Completed | Early Case | MC776-5 (RLWI) INTERV | 2020-05-14 | 2020-06-08 | 17 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW |  | Early
Completed | Early Case | MC777-3 (RLWI) BWM | 2020-06-08 | 2020-06-15 | 7 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC777-3 (RLWI) INTERV | 2020-06-15 | 2020-06-30 | 21 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW |  | Early
Completed | Early Case | MC822-11 (RLWI) BWM | 2020-06-30 | 2020-07-09 | 9 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-11 (RLWI) INTERV | 2020-07-09 | 2020-07-20 | 10 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW |  | Early
Completed | Early Case | REMOB | 2020-12-21 | 2021-01-07 | 14 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM |  | MOB | Early
Completed | Early Case | DC124 (RLWI) BWM | 2021-01-07 | 2021-01-08 | 3 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC124 (RLWI) INTERV | 2021-01-08 | 2021-02-11 | 23 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC121 (RLWI) BWM | 2021-02-11 | 2021-02-19 | 8 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC121 (RLWI) INTERV | 2021-02-19 | 2021-03-06 | 15 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC114 (RLWI) BWM | 2021-03-06 | 2021-03-11 | 8 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC114 (RLWI) INTERV | 2021-03-11 | 2021-04-12 | 17 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | Isabela 1 (RLWI) BWM | 2021-04-12 | 2021-05-04 | 8 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | Isabela 1 (RLWI) INTERV | 2021-05-04 | 2021-06-07 | 23 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | BWM at Dock Stim for all NK wells (Charge to A-1 AFE) | 2021-06-07 | 2021-07-03 | 12 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | A-3 (RLWI) INTERV | 2021-07-03 | 2021-07-11 | 8 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | A-1 (RLWI) BWM | 2021-07-11 | 2021-07-13 | 2 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC429-A1 (A-1) (RLWI) INTERV | 2021-07-13 | 2021-07-18 | 7 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | F-5 (RLWI) BWM | 2021-07-18 | 2021-07-20 | 2 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | F-5 (RLWI) INTERV | 2021-07-20 | 2021-07-26 | 7 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | WOW | 2021-07-26 | 2021-09-20 | 10 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM |  | WOW | Early
Completed | Early Case | 5 YEAR DRY DOCK (RLWI) BWM | 2021-09-20 | 2021-11-04 | 42 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-11 (SB8) BWM | 2021-11-04 | 2021-11-14 | 10 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-11 (SB8) Baker Hughes 7.2 LWIS (RLWI) INTERV | 2021-11-14 | 2022-01-02 | 31 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-7 (SB3) (RLWI) BWM | 2022-01-02 | 2022-01-12 | 10 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-14 (SB6) WSJI (RLWI) INTERV | 2022-01-12 | 2022-02-03 | 27 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-8 (SB5) (RLWI) BWM | 2022-02-03 | 2022-02-09 | 6 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-8 (SB5) WSJI (RLWI) INTERV | 2022-02-09 | 2022-03-01 | 20 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC776-6 (RLWI) BWM | 2022-03-01 | 2022-03-08 | 7 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC776-6 Caltex RST (RLWI) INTERV | 2022-03-08 | 2022-03-19 | 9 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC133 (RLWI) BWM | 2022-03-19 | 2022-03-29 | 8 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC133 Mars choke insert (RLWI) INTERV | 2022-03-29 | 2022-04-11 | 13 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC311 (RLWI) BWM | 2022-04-11 | 2022-04-18 | 7 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC311 Mars choke insert (RLWI) INTERV | 2022-04-18 | 2022-04-24 | 13 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-10 WSJI BWM | 2022-04-24 | 2022-05-05 | 5 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-10 WSJI INTERV | 2022-05-05 | 2022-05-15 | 16 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-7 WSJI INTERV | 2022-05-15 | 2022-05-24 | 10 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-15 WSJI BWM | 2022-05-24 | 2022-05-26 | 2 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-15 WSJI INTERV | 2022-05-26 | 2022-06-06 | 16 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC777-3 BWM (RLWI) INTERV | 2022-06-06 | 2022-06-11 | 5 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC777-3 (RLWI) PH INTERV | 2022-06-11 | 2022-06-20 | 9 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC776-5 (RLWI) PH INTERV | 2022-06-20 | 2022-07-01 | 10 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | White Space | 2022-07-01 | 2022-07-13 | 12 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM |  | WS | Early
Completed | Early Case | MC822-3 BWM (RLWI) INTERV | 2022-07-13 | 2022-08-03 | 14 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | PDQ P2 Flowline jumper replacement BWM | 2022-08-03 | 2022-08-07 | 4 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-3 BWM (RLWI) INTERV | 2022-08-07 | 2022-08-14 | 3 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-3 (RLWI) BH INTERV | 2022-08-14 | 2022-10-02 | 24 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC122 BWM (RLWI) BH INTERV | 2022-10-02 | 2022-10-17 | 7 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC122 (RLWI) INTERV | 2022-10-17 | 2023-01-29 | 42 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-17 BWM (RLWI) INTERV | 2023-01-30 | 2023-02-11 | 7 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-17 (SB7) (RLWI) INTERV | 2023-02-11 | 2023-03-18 | 26 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-11 BWM (RLWI) INTERV | 2023-03-18 | 2023-03-24 | 2 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-11 (SB8) INTERV | 2023-03-24 | 2023-04-16 | 17 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | BWM LSPS Flushing (RLWI) INTERV | 2023-04-16 | 2023-04-21 | 7 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | BWM LSPS Flushing (RLWI) INTERV | 2023-04-21 | 2023-04-24 | 3 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | F-2 (RLWI) INTERV (No SG1) | 2023-04-24 | 2023-05-09 | 13 | GOM.Nakika | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC801 BWM (RLWI) INTERV | 2023-05-09 | 2023-05-15 | 6 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC801 (RLWI) INTERV | 2023-05-15 | 2023-06-12 | 27 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC775-3 (NPi13) (RLWI) BWM | 2023-06-12 | 2023-06-18 | 6 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC775-3 (NPi13) (RLWI) INTERV | 2023-06-18 | 2023-07-07 | 12 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC314 BWM (RLWI) INTERV | 2023-07-07 | 2023-07-22 | 6 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC314 (RLWI) INTERV | 2023-07-22 | 2023-08-01 | 28 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | Shell Farm Out | 2023-08-01 | 2023-08-29 | 22 | GOM.Region | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | WOW LOOP CURRENTS | 2023-08-29 | 2023-09-25 | 29 | GOM.Region | GOM.LWI.ISLVEN | GOM | X | WOW | Early
Completed | Early Case | DC124 BWM (RLWI) INTERV | 2023-09-25 | 2023-10-01 | 4 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC124 (RLWI) INTERV | 2023-10-01 | 2024-01-01 | 25 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-3 INTERV | 2024-01-01 | 2024-02-10 | 37 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC314 MP (RLWI) INTERV | 2024-02-10 | 2024-03-15 | 29 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | White Space | 2024-03-15 | 2024-04-03 | 19 | GOM.Region | GOM.LWI.ISLVEN | GOM |  | WS | Early
Completed | Early Case | ATL/NK Farm out | 2024-04-03 | 2024-07-07 | 95 | GOM.Region | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | BWM (RLWI) INTERV | 2024-07-07 | 2024-08-07 | 31 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC112 (RLWI) INTERV | 2024-08-07 | 2024-09-05 | 14 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | MC822-22 BWM | 2024-09-05 | 2024-09-11 | 6 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | MC822-22 (RLWI) INTERV | 2024-09-11 | 2024-11-01 | 24 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC322 Baker Hughes 7.2 LWIS (RLWI) INTERV | 2024-11-01 | 2024-12-09 | 25 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC214 BWM (RLWI) INTERV | 2024-12-09 | 2024-12-15 | 6 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC214 (RLWI) INTERV | 2024-12-15 | 2025-01-03 | 16 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC311 (RLWI) INTERV | 2025-01-03 | 2025-01-18 | 18 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | TH T41 Flushing(RLWI) INTERV | 2025-01-18 | 2025-01-23 | 5 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC131 (RLWI) INTERV | 2025-01-23 | 2025-02-07 | 15 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC122 (RLWI) INTERV | 2025-02-07 | 2025-02-09 | 2 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC111 (RLWI) INTERV | 2025-02-09 | 2025-02-10 | 3 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC133 BWM (RLWI) INTERV | 2025-02-10 | 2025-02-13 | 4 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC133 (RLWI) INTERV | 2025-02-13 | 2025-02-17 | 4 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | Thunder Horse Pumping | 2025-02-17 | 2025-03-25 | 30 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | RM | Early
Completed | Early Case | A-5 INTERV | 2018-12-22 | 2019-01-24 | 10 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW |  | Early
Completed | Early Case | BWM | 2019-01-24 | 2019-02-21 | 19 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | GC782-16 (MD16) RES DRL | 2019-02-21 | 2019-05-04 | 65 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM |  | DRL | Early
Completed | Early Case | ARD/Risers/BOP BWM | 2019-05-04 | 2019-05-14 | 19 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | GC782-16 (MD16) CPL | 2019-05-14 | 2019-10-12 | 84 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM |  | CPL | Early
Completed | Early Case | Integrity Management Repairs | 2019-10-12 | 2019-11-10 | 22 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | RM | Early
Completed | Early Case | A-4 INTERV | 2019-11-10 | 2019-12-01 | 29 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW |  | Early
Completed | Early Case | A-12 INTERV CT | 2019-12-01 | 2019-12-10 | 9 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW |  | Early
Completed | Early Case | Integrity Maintenance | 2019-12-10 | 2019-12-18 | 8 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | RM | Early
Completed | Early Case | MD 2019 Outage (PLACEHOLDER) | 2019-12-18 | 2019-12-23 | 5 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | OTH | Early
Completed | Early Case | Integrity Maintenance | 2019-12-23 | 2020-01-23 | 24 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | RM | Early
Completed | Early Case | A-12 INTERV PLT | 2020-01-23 | 2020-02-08 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW |  | Early
Completed | Early Case | A-8 INTERV | 2020-02-08 | 2020-02-27 | 14 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW |  | Early
Completed | Early Case | A-11 INTERV | 2020-02-27 | 2020-03-03 | 10 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW |  | Early
Completed | Early Case | A-4 INTERV | 2020-03-03 | 2020-03-06 | 8 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW |  | Early
Completed | Early Case | BWM | 2020-03-06 | 2020-03-31 | 6 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | A10 INTERV | 2020-07-20 | 2020-07-25 | 14 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW |  | Early
Completed | Early Case | A-2 TREE REPLACEMENT INTERV | 2020-10-18 | 2020-11-07 | 13 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Completed | Early Case | A-12 INTERV | 2021-04-12 | 2021-04-24 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Completed | Early Case | A-1 INTERV | 2021-04-24 | 2021-04-28 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Completed | Early Case | Pre | 2021-05-17 | 2021-05-24 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | MAD DOG OUTAGE | 2021-05-24 | 2021-05-31 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | Post | 2021-05-31 | 2021-06-07 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | Pre | 2021-12-28 | 2022-02-15 | 21 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | MAD DOG OUTAGE | 2022-02-15 | 2022-02-27 | 12 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | Post | 2022-02-27 | 2022-03-13 | 11 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | BWM/Derrick deck repairs and Equipment overhauls | 2022-03-13 | 2022-05-01 | 6 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | GC782-14 MD14 (A-13) DRL | 2022-05-01 | 2022-12-15 | 148 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2022-12-15 | 2023-02-15 | 62 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | A12, A7, and A11 INTERV | 2023-02-15 | 2023-03-16 | 21 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWP | Early
Completed | Early Case | BWM BOP Annular Element Change out | 2023-03-16 | 2023-03-20 | 4 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | GC782-14 MD14 (A-13) ST DRL | 2023-03-20 | 2023-11-19 | 90 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2023-11-19 | 2023-12-05 | 10 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | GC782-14 MD14 (A-13) ST2 DRL | 2023-12-05 | 2024-01-30 | 64 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | MPP | DRL | Early
Completed | Early Case | White Space | 2024-01-30 | 2024-02-06 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM |  | WS | Early
Completed | Early Case | BWM | 2024-02-06 | 2024-04-13 | 40 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | A-4 INTERV | 2024-04-13 | 2024-05-18 | 27 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWP | Early
Completed | Early Case | A-12 INTERV | 2024-05-18 | 2024-06-26 | 25 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWP | Early
Completed | Early Case | A-7 INTERV | 2024-06-27 | 2024-07-23 | 19 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWP | Early
Completed | Early Case | BWM IM | 2024-07-23 | 2024-09-17 | 63 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Completed | Early Case | Pre | 2024-09-17 | 2024-10-24 | 28 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | MAD DOG OUTAGE | 2024-10-24 | 2024-11-10 | 17 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | Post | 2024-11-10 | 2024-11-23 | 11 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Completed | Early Case | MD17 (M20) DRL | 2024-11-23 | 2025-04-20 | 153 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Completed | Early Case | A7 GL | 2025-02-01 | 2025-02-21 | 33 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
In Progress | Early Case | MD17 (M20) CPL | 2025-04-20 | 2025-08-27 | 92 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | Rig Maintenance C3 | 2025-08-27 | 2025-08-30 | 3 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Not Started | Early Case | White Space | 2025-08-30 | 2025-11-22 | 84 | GOM.Region | GOM.Mad Dog SPAR | GOM | X | WS | Early
Not Started | Early Case | A10 WL INTERV | 2025-11-22 | 2025-12-01 | 9 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | MD15 (A13) DRL | 2025-12-01 | 2026-05-15 | 165 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Not Started | Early Case | A5 WH Seal Repair INTERV | 2025-12-01 | 2025-12-08 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | A10 Pump INTERV | 2026-02-28 | 2026-03-22 | 22 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | MD15 (A13) CPL | 2026-05-15 | 2026-08-16 | 93 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | MD14 New top hole DRL | 2026-08-16 | 2027-01-23 | 160 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Not Started | Early Case | MD14 New Top Hole CPL | 2027-01-23 | 2027-04-26 | 93 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | MAD DOG TAR | 2027-04-26 | 2027-05-28 | 32 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Not Started | Early Case | TBD WSO pump & WL PH INTERV | 2027-05-08 | 2027-06-07 | 30 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | GC782-8 A-6 ST De-CPL | 2027-05-28 | 2027-07-17 | 50 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | GC782-8 A-6 ST-DRL | 2027-07-17 | 2027-09-05 | 50 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Not Started | Early Case | A-6 ST CPL | 2027-09-05 | 2027-11-26 | 82 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | GC782-7 A-4 ST-DRL | 2027-11-26 | 2028-03-05 | 100 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Not Started | Early Case | GC782-7 A-4 CPL | 2028-03-05 | 2028-04-24 | 50 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | TBD WSO pump & WL PH INTERV | 2028-03-10 | 2028-04-09 | 30 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | MD14 (A13) P&A | 2028-04-24 | 2028-06-08 | 45 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | P&A | Early
Not Started | Early Case | Rig Maintenance Pull ODR | 2028-06-08 | 2028-06-22 | 14 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Not Started | Early Case | TBD WSO pump & WL PH INTERV | 2029-01-04 | 2029-02-03 | 30 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Completed | Early Case | Pre-TAR | 2019-01-01 | 2019-02-07 | 31 | GOM.Thunder Horse | GOM.PDQ | GOM |  | RM | Early
Completed | Early Case | TAR | 2019-02-07 | 2019-03-04 | 25 | GOM.Thunder Horse | GOM.PDQ | GOM |  | RM | Early
Completed | Early Case | Post-TAR | 2019-03-04 | 2019-03-18 | 19 | GOM.Thunder Horse | GOM.PDQ | GOM |  | RM | Early
Completed | Early Case | MC822-15 (SB12) (CWOR) INTERV | 2019-03-18 | 2019-05-16 | 41 | GOM.Thunder Horse | GOM.PDQ | GOM | WW |  | Early
Completed | Early Case | MC778-2 (SPi5) (CWOR) RE-CPL INTERV | 2019-05-16 | 2019-06-23 | 28 | GOM.Thunder Horse | GOM.PDQ | GOM | WW |  | Early
Completed | Early Case | BWM | 2019-06-23 | 2019-08-11 | 19 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC822-16 (SB2) DRL RES | 2019-08-11 | 2019-12-10 | 27 | GOM.Thunder Horse | GOM.PDQ | GOM |  | DRL | Early
Completed | Early Case | BWM | 2019-12-10 | 2019-12-28 | 10 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | Crane Repairs | 2019-12-28 | 2020-02-16 | 25 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | RM | Early
Completed | Early Case | MC778-2 (SPi5) (CWOR) RE-CPL INTERV | 2020-02-16 | 2020-05-20 | 28 | GOM.Thunder Horse | GOM.PDQ | GOM | WW |  | Early
Completed | Early Case | MC822-16 (SB2) DRL ST (TA) | 2020-07-22 | 2020-12-03 | 58 | GOM.Thunder Horse | GOM.PDQ | GOM |  | DRL | Early
Completed | Early Case | MC822-7 CWOR INTERV | 2020-12-04 | 2020-12-17 | 13 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWI | Early
Completed | Early Case | BWM | 2021-03-09 | 2021-03-15 | 6 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | SX2 tie-in and PDQ outage | 2021-03-15 | 2021-05-06 | 52 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | TAR | Early
Completed | Early Case | BWM | 2021-05-06 | 2021-05-07 | 1 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | Rig Upgrade | 2021-09-14 | 2021-11-13 | 45 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM | 2021-11-13 | 2021-11-20 | 7 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC778-1 P&A (PDQ) | 2021-11-20 | 2022-01-11 | 34 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWI | Early
Completed | Early Case | BWM Switch from BOP to CWOR | 2022-01-11 | 2022-02-18 | 23 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC822-9 CWOR/CETCO P&A (PDQ) | 2022-03-01 | 2022-03-07 | 20 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWI | Early
Completed | Early Case | TH 778-2 (SPi4) CWOR INTERV (PDQ) | 2022-03-07 | 2022-03-16 | 10 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
Completed | Early Case | MC822-5 CWOR (SB3) INTERV | 2022-03-16 | 2022-04-20 | 17 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | IAT | Early
Completed | Early Case | BWM Switch from CWOR to BOP | 2022-04-20 | 2022-05-17 | 14 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC822-5 CWOR (SB3) INTERV | 2022-05-17 | 2022-08-06 | 45 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | IAT | Early
Completed | Early Case | RIG MOVE Tree Swaps | 2022-08-06 | 2022-08-08 | 2 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM MC778-2 (SPi4) | 2022-08-06 | 2022-09-07 | 14 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC778-2 (SPi4) CPL (PDQ) BOP | 2022-09-07 | 2022-11-29 | 36 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | CPL | Early
Completed | Early Case | RIG MOVE Tree Swaps | 2022-11-29 | 2022-12-04 | 4 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC822-9 P&A BOP (PDQ) | 2022-12-04 | 2023-03-05 | 46 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWI | Early
Completed | Early Case | BWM SWITCH BOP TO CWOR | 2023-03-05 | 2023-03-12 | 7 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM CWOR DECK TEST | 2023-03-12 | 2023-05-09 | 18 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC778-2 PLT/CTU INTERV (PDQ) | 2023-05-09 | 2023-06-12 | 23 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
Completed | Early Case | BWM (PDQ) Rig Maintenance | 2023-06-12 | 2023-08-19 | 62 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM | 2023-08-19 | 2023-08-20 | 8 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC778-16 (SPi5) D (PDQ) | 2023-08-20 | 2024-01-14 | 80 | GOM.Thunder Horse | GOM.PDQ | GOM | DVP | DRL | Early
Completed | Early Case | MC778-16 SPi5 CPL (PDQ) | 2024-01-14 | 2024-03-22 | 52 | GOM.Thunder Horse | GOM.PDQ | GOM | DVP | CPL | Early
Completed | Early Case | BWM (laying out BOP and picking up CWOR) | 2024-03-22 | 2024-03-29 | 7 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM (CWOR deck test) | 2024-03-29 | 2024-04-17 | 16 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC822-7 INTERV (PDQ) | 2024-04-17 | 2024-06-10 | 15 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
Completed | Early Case | BWM Rig Maintenance | 2024-06-10 | 2024-08-06 | 41 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM Crane Boom Changeout | 2024-08-06 | 2024-09-05 | 30 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM Rig Maintenance | 2024-09-05 | 2024-09-23 | 18 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM Laying out CWOR and Picking up BOP | 2024-09-23 | 2024-10-14 | 10 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC822-6 PA | 2024-10-14 | 2024-12-15 | 32 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | P&A | Early
Completed | Early Case | BWM Rig Maintenance | 2024-12-15 | 2025-01-17 | 33 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM (laying out BOP and picking up CWOR) | 2025-01-17 | 2025-01-24 | 7 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM (CWOR deck test) | 2025-01-24 | 2025-02-20 | 27 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC778-2 (PDQ) INTERV | 2025-02-20 | 2025-03-26 | 18 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
Completed | Early Case | MC822-4 (PDQ) INTERV | 2025-03-26 | 2025-04-06 | 11 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
Completed | Early Case | MC822-7 (PDQ) INTERV | 2025-04-06 | 2025-04-18 | 15 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
In Progress | Early Case | BWM (CWOR deck test) | 2025-04-18 | 2025-09-24 | 143 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Not Started | Early Case | MC778-8 PXA Open Water Work (PDQ) INTERV | 2025-09-24 | 2025-10-01 | 7 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | P&A | Early
Not Started | Early Case | SPi7/8 DRL (PDQ) | 2025-10-01 | 2026-01-30 | 121 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | DRL | Early
Not Started | Early Case | White Space | 2026-01-30 | 2026-03-01 | 30 | GOM.Region | GOM.PDQ | GOM | X | WS | Early
Not Started | Early Case | TAR | 2026-03-01 | 2026-05-19 | 79 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | TAR | Early
Not Started | Early Case | SPi7/8 CPL (PDQ) | 2026-05-19 | 2026-08-19 | 92 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | CPL | Early
Not Started | Early Case | Rig Maintenance | 2026-08-19 | 2026-09-18 | 30 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Not Started | Early Case | MC822-4 PXA (PDQ) INTERV | 2026-09-18 | 2026-11-27 | 70 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | P&A | Early
Not Started | Early Case | White Space | 2026-11-27 | 2027-01-01 05:20 | 35 | GOM.Region | GOM.PDQ | GOM | X | WS | Early
Not Started | Early Case | SPi11/6 DRL (PDQ) | 2027-01-01 05:20 | 2027-05-11 05:20 | 130 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | DRL | Early
Not Started | Early Case | SPi11/6 CPL (PDQ) | 2027-05-11 05:20 | 2027-08-09 05:20 | 90 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | CPL | Early
Not Started | Early Case | Rig Maintenance | 2027-08-09 05:20 | 2027-09-08 05:20 | 30 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Not Started | Early Case | SPi4/5w DRL | 2027-09-08 05:20 | 2028-01-16 05:20 | 130 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | DRL | Early
Not Started | Early Case | SPi4/5w CPL | 2028-01-16 05:20 | 2028-04-15 05:20 | 90 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | CPL | Early
Not Started | Early Case | Rig Maintenance | 2028-04-15 05:20 | 2028-07-14 05:20 | 90 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Not Started | Early Case | Rig Start up | 2025-10-01 | 2025-10-09 | 8 | GOM.Region | GOM.Q5000 | GOM | WW | RSU | Early
Not Started | Early Case | MC822-3 (RLWI) INTERV | 2025-10-09 | 2025-10-30 | 21 | GOM.Thunder Horse | GOM.Q5000 | GOM | WW | WWP | Early
Not Started | Early Case | Thunder Horse P45 C/O | 2025-10-30 | 2025-11-14 | 15 | GOM.Thunder Horse | GOM.Q5000 | GOM | WW | WWP | Early
Not Started | Early Case | Rig Start up | 2026-01-01 | 2026-01-09 | 8 | GOM.Region | GOM.TBD #02 | GOM | WW | RSU | Early
Not Started | Early Case | Restoration Place Holder INTERV | 2026-01-09 | 2026-02-13 | 35 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Early
Not Started | Early Case | White Space | 2026-02-13 | 2027-01-01 | 322 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Early
Not Started | Early Case | Restoration Place Holder INTERV | 2027-01-01 | 2027-06-30 | 180 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Early
Not Started | Early Case | White Space | 2027-06-30 | 2028-01-01 | 185 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Early
Not Started | Early Case | Restoration Place Holder INTERV | 2028-01-01 | 2028-06-29 | 180 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Early
Not Started | Early Case | White Space | 2028-06-29 | 2029-01-01 | 186 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Early
Not Started | Early Case | Restoration Place Holder INTERV | 2029-01-01 | 2029-06-30 | 180 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Early
Not Started | Early Case | Rig Start up | 2026-04-01 | 2026-05-06 | 35 | GOM.Region | GOM.TBD #07 | GOM | WW | RSU | Early
Not Started | Early Case | DC105 (MFXB75) DRL | 2026-05-06 | 2026-07-05 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | DRL | Early
Not Started | Early Case | DC105 (MFXB75) CPL | 2026-07-05 | 2026-08-24 | 50 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | CPL | Early
Not Started | Early Case | ATL DC152 DRL | 2026-08-24 | 2026-10-10 | 47 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Early
Not Started | Early Case | ATL DC152 CPL | 2026-10-10 | 2026-11-13 | 34 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | DC106 (MFXN54) DRL | 2026-11-13 | 2026-12-23 | 40 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | DRL | Early
Not Started | Early Case | DC106 (MFXN54) CPL | 2026-12-23 | 2027-01-27 | 35 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | CPL | Early
Not Started | Early Case | DC123 RE-CPL | 2027-01-27 | 2027-03-28 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | Isabela 1 (I-1) PA | 2027-03-28 | 2027-05-23 | 56 | GOM.Nakika | GOM.TBD #07 | GOM | WW | P&A | Early
Not Started | Early Case | NBr7 BWM | 2027-05-23 | 2027-05-25 | 2 | GOM.Thunder Horse | GOM.TBD #07 | GOM | X | RM | Early
Not Started | Early Case | NBr7 DRL | 2027-05-25 | 2027-09-10 | 108 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | DRL | Early
Not Started | Early Case | NBr7 CPL | 2027-09-10 | 2027-10-25 | 45 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | CPL | Early
Not Started | Early Case | Far South 2 Appraisal DRL | 2027-10-25 | 2028-02-02 | 100 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Early
Not Started | Early Case | ATL ST PH DRL #1 | 2028-02-02 | 2028-04-02 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Early
Not Started | Early Case | ATL ST PH CPL #1 | 2028-04-02 | 2028-05-02 | 30 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | ATL ST PH DRL #2 | 2028-05-02 | 2028-07-01 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Early
Not Started | Early Case | ATL ST PH CPL #2 | 2028-07-01 | 2028-07-31 | 30 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | NPi18 DRL | 2028-07-31 | 2028-11-13 | 105 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | DRL | Early
Not Started | Early Case | NPi18 CPL | 2028-11-13 | 2028-12-28 | 45 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | CPL | Early
Not Started | Early Case | MC775-3 (NPi13) PA | 2028-12-28 | 2029-01-27 | 30 | GOM.Thunder Horse | GOM.TBD #07 | GOM | WW | P&A | Early
Not Started | Early Case | APOLLO DRL | 2029-01-27 | 2029-04-27 | 90 | GOM.GOMX | GOM.TBD #07 | GOM | MPP | DRL | Early
Not Started | Early Case | ATL ST PH DRL #3 | 2029-04-27 | 2029-06-26 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | MPP | DRL | Early
Not Started | Early Case | ATL ST PH CPL #3 | 2029-06-26 | 2029-07-26 | 30 | GOM.Atlantis | GOM.TBD #07 | GOM | MPP | CPL | Early
Not Started | Early Case | ATL ST PH4 ST DRL | 2029-07-26 | 2029-09-12 | 48 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Early
Not Started | Early Case | ATL ST PH4 ST CPL | 2029-09-12 | 2029-10-17 | 35 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | Exploration PH6 DRL | 2029-10-17 | 2030-01-15 | 90 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Early
Not Started | Early Case | Exploration PH7 DRL | 2030-01-15 | 2030-04-15 | 90 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Early
Not Started | Early Case | Exploration PH8 DRL | 2030-04-15 | 2030-07-14 | 90 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Early
Completed | Early Case | GC826-7 (SP12) DRL | 2018-09-30 | 2018-12-18 | 42 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | Batch GC825-7 (SWP2) DRL | 2018-12-18 | 2018-12-26 | 42 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | GC826-8 (SP2) DRL | 2018-12-26 | 2019-02-08 | 37 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2019-02-08 | 2019-02-09 | 1 | GOM.Argos | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | GC825-7 (SWP2) DRL | 2019-02-09 | 2019-03-09 | 34 | GOM.Argos | GOM.West Auriga | GOM | DVP | DRL | Early
Completed | Early Case | BWM | 2019-03-09 | 2019-03-13 | 4 | GOM.Argos | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | Batch Set | 2019-03-13 | 2019-04-04 | 16 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | GC826-09 (SI2) DRL | 2019-04-04 | 2019-04-18 | 6 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2019-04-18 | 2019-04-20 | 2 | GOM.Argos | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | GC826-9 (SI2) DRL | 2019-04-20 | 2019-07-06 | 40 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2019-07-06 | 2019-07-07 | 2 | GOM.Argos | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | GC826-10 (SWP1) DRL | 2019-07-07 | 2019-08-28 | 27 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2019-08-28 | 2019-09-02 | 2 | GOM.Argos | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | GC869-3 (SP7) RESPUD 1 | 2019-09-02 | 2019-09-28 | 28 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2019-09-28 | 2019-10-03 | 2 | GOM.Argos | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | SP4 TOPHOLE DRL | 2019-10-03 | 2019-10-07 | 8 | GOM.Argos | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | Subsea Tree BWM | 2019-10-07 | 2019-10-11 | 2 | GOM.Argos | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | BWM | 2019-10-11 | 2019-10-14 | 4 | GOM.GOMX | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | Core X DRL | 2019-10-14 | 2020-01-10 | 50 | GOM.GOMX | GOM.West Auriga | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2020-01-10 | 2020-01-20 | 4 | GOM.Argos | GOM.West Auriga | GOM | X | RM | Early
Completed | Early Case | GC825-4 (SP10) CPL | 2020-01-20 | 2020-02-27 | 35 | GOM.Argos | GOM.West Auriga | GOM | MPP | CPL | Early
Completed | Early Case | GC825-6 (SP5) CPL | 2020-02-27 | 2020-04-16 | 35 | GOM.Argos | GOM.West Auriga | GOM | OTH | CPL | Early
Completed | Early Case | GC826-7 (SP12) CPL | 2020-04-16 | 2020-05-19 | 35 | GOM.Argos | GOM.West Auriga | GOM | MPP | CPL | Early
Completed | Early Case | GC825-2 (SP14) CPL | 2020-05-20 | 2020-07-08 | 32 | GOM.Argos | GOM.West Auriga | GOM | MPP | CPL | Early
Completed | Early Case | GC826-8 (SP2) CPL | 2020-07-08 | 2020-08-12 | 32 | GOM.Argos | GOM.West Auriga | GOM | MPP | CPL | Early
Completed | Early Case | GC826-6 (SP9) CPL | 2020-08-12 | 2020-10-27 | 32 | GOM.Argos | GOM.West Auriga | GOM | MPP | CPL | Early
Completed | Early Case | Demob | 2020-10-27 | 2020-11-05 | 7 | GOM.Region | GOM.West Auriga | GOM | DVP | MOB | Early
Completed | Early Case | Exp |  | 2020-10-27 | 0 | GOM.Region | GOM.West Auriga | GOM | OTH | IAC | Early
Completed | Early Case | 520-4 (Manuel 2) DRL | 2018-12-28 | 2019-02-21 | 13 | GOM.Nakika | GOM.West Capricorn | GOM | DVP | DRL | Early
Completed | Early Case | H5 DRL | 2019-02-21 | 2019-04-06 | 44 | GOM.Nakika | GOM.West Capricorn | GOM | EXP | DRL | Early
Completed | Early Case | H5 LT DRL | 2019-04-06 | 2019-04-23 | 9 | GOM.Nakika | GOM.West Capricorn | GOM | EXP | DRL | Early
Completed | Early Case | Demob | 2019-04-23 | 2019-04-30 | 10 | GOM.Region | GOM.West Capricorn | GOM | OTH | RM | Early
Completed | Early Case | Exp | 2019-04-30 | 2019-04-30 | 0 | GOM.Region | GOM.West Capricorn | GOM |  |  | Early
Completed | Early Case | NPi14 CPL | 2018-11-22 | 2019-01-03 | 41 | GOM.Thunder Horse | GOM.West Vela | GOM | DVP | CPL | Early
Completed | Early Case | MC777-4 INTERV | 2019-01-03 | 2019-01-11 | 7 | GOM.Thunder Horse | GOM.West Vela | GOM | WW | RM | Early
Completed | Early Case | BWM | 2019-01-11 | 2019-01-13 | 4 | GOM.Nakika | GOM.West Vela | GOM | X | RM | Early
Completed | Early Case | A6 DRL | 2019-01-13 | 2019-02-07 | 19 | GOM.Nakika | GOM.West Vela | GOM | MPP | DRL | Early
Completed | Early Case | WS | 2019-02-07 | 2019-02-18 | 14 | GOM.Nakika | GOM.West Vela | GOM | X |  | Early
Completed | Early Case | A7 DRL | 2019-02-18 | 2019-03-14 | 22 | GOM.Nakika | GOM.West Vela | GOM | MPP | DRL | Early
Completed | Early Case | A7 CPL | 2019-03-14 | 2019-04-27 | 36 | GOM.Nakika | GOM.West Vela | GOM | MPP | CPL | Early
Completed | Early Case | BWM | 2019-04-27 | 2019-04-30 | 2 | GOM.Nakika | GOM.West Vela | GOM | X | RM | Early
Completed | Early Case | H6 DRL | 2019-04-30 | 2019-05-27 | 26 | GOM.GOMX | GOM.West Vela | GOM | EXP | DRL | Early
Completed | Early Case | BWM | 2019-05-27 | 2019-05-31 | 4 | GOM.Thunder Horse | GOM.West Vela | GOM | X | RM | Early
Completed | Early Case | MC777-4 INTERV | 2019-05-31 | 2019-06-08 | 7 | GOM.Thunder Horse | GOM.West Vela | GOM | WW |  | Early
Completed | Early Case | MC776-9 (NPi5W) WI DRL | 2019-06-08 | 2019-08-25 | 48 | GOM.Thunder Horse | GOM.West Vela | GOM | DVI | DRL | Early
Completed | Early Case | MC776-9 (NPi5W) CPL | 2019-08-25 | 2019-10-18 | 52 | GOM.Thunder Horse | GOM.West Vela | GOM | DVI | CPL | Early
Completed | Early Case | BWM | 2019-10-18 | 2019-10-20 | 4 | GOM.Atlantis | GOM.West Vela | GOM | X | RM | Early
Completed | Early Case | ATL3 Batch DRL | 2019-10-20 | 2019-11-25 | 19 | GOM.Atlantis | GOM.West Vela | GOM | MPP | DRL | Early
Completed | Early Case | BWM | 2019-11-25 | 2019-11-27 | 2 | GOM.GOMX | GOM.West Vela | GOM | X | RM | Early
Completed | Early Case | JW1 DRL | 2019-11-27 | 2019-12-22 | 15 | GOM.GOMX | GOM.West Vela | GOM | EXP | DRL | Early
Completed | Early Case | DC223 (Un54) DRL | 2019-12-22 | 2020-03-08 | 27 | GOM.Atlantis | GOM.West Vela | GOM | DVP | DRL | Early
Completed | Early Case | DC224 (J80) DRL | 2020-03-08 | 2020-04-21 | 31 | GOM.Atlantis | GOM.West Vela | GOM | DVP | DRL | Early
Completed | Early Case | DC212 (E54 ) DRL | 2020-04-21 | 2020-05-23 | 23 | GOM.Atlantis | GOM.West Vela | GOM | DVP | DRL | Early
Completed | Early Case | DC212 (E57) CPL | 2020-05-23 | 2020-07-14 | 26 | GOM.Atlantis | GOM.West Vela | GOM | DVP | CPL | Early
Completed | Early Case | DC221 (nW54) DRL | 2020-07-14 | 2020-10-19 | 23 | GOM.Atlantis | GOM.West Vela | GOM | DVP | DRL | Early
Completed | Early Case | DC221 (nW54) CPL | 2020-10-19 | 2020-12-20 | 35 | GOM.Atlantis | GOM.West Vela | GOM | DVP | CPL | Early
Completed | Early Case | GC743 DC213 (V54 ) DRL | 2020-12-20 | 2021-01-23 | 23 | GOM.Atlantis | GOM.West Vela | GOM | DVP | DRL | Early
Completed | Early Case | GC743 DC213 (V54) CPL | 2021-01-23 | 2021-02-23 | 35 | GOM.Atlantis | GOM.West Vela | GOM | DVP | CPL | Early
Completed | Early Case | AT GC743-2 P&A | 2021-02-23 | 2021-03-18 | 18 | GOM.Atlantis | GOM.West Vela | GOM | OTH | P&A | Early
Completed | Early Case | AT DC211 P&A | 2021-03-18 | 2021-04-11 | 16 | GOM.Atlantis | GOM.West Vela | GOM | OTH | P&A | Early
Completed | Early Case | BWM MPD SIT & BOP's | 2021-04-11 | 2021-04-21 | 10 | GOM.Mad Dog | GOM.West Vela | GOM | X | RM | Early
Completed | Early Case | MD GC826-1 P&A | 2021-04-21 | 2021-04-30 | 17 | GOM.Mad Dog | GOM.West Vela | GOM | OTH | P&A | Early
Completed | Early Case | MD GC826-3 P&A | 2021-04-30 | 2021-05-26 | 31 | GOM.Mad Dog | GOM.West Vela | GOM | OTH | P&A | Early
Completed | Early Case | Demob | 2021-05-26 | 2021-05-31 | 5 | GOM.Region | GOM.West Vela | GOM | OTH | RM | Early
Completed | Early Case | START UP | 2023-01-29 | 2023-04-18 | 52 | GOM.Region | GOM.West Vela | GOM | X | RSU | Early
Completed | Early Case | BWM MOB | 2023-04-18 | 2023-05-06 | 10 | GOM.Region | GOM.West Vela | GOM | X | RM | Early
Completed | Early Case | MD213 (SP5) Isolation INTERV | 2023-05-06 | 2023-05-13 | 3 | GOM.Argos | GOM.West Vela | GOM | WW | WWI | Early
Completed | Early Case | GC826-8 MD123 (SP2) Pull Upper Completion INTERV | 2023-05-13 | 2023-06-06 | 16 | GOM.Argos | GOM.West Vela | GOM | WW | WWI | Early
Completed | Early Case | GC826-6 MD113 (SP9) Pull Upper Completion INTERV | 2023-06-06 | 2023-06-15 | 16 | GOM.Argos | GOM.West Vela | GOM | WW | WWI | Early
Completed | Early Case | GC826-6 MD113 (SP9) UPPER CPL | 2023-06-15 | 2023-06-26 | 12 | GOM.Argos | GOM.West Vela | GOM | MPP | CPL | Early
Completed | Early Case | GC826-8 MD123 (SP2) UPPER CPL | 2023-06-26 | 2023-07-07 | 12 | GOM.Argos | GOM.West Vela | GOM | MPP | CPL | Early
Completed | Early Case | GC825-2 MD111 (SP14) Pull Upper Completion INTERV | 2023-07-07 | 2023-07-22 | 11 | GOM.Argos | GOM.West Vela | GOM | WW | WWI | Early
Completed | Early Case | GC825-2 MD111 (SP14) UPPER CPL | 2023-07-22 | 2023-08-04 | 9 | GOM.Argos | GOM.West Vela | GOM | MPP | CPL | Early