## MEAN CASE
Activity Status | (*)WBS Name | Activity Name | GWDXAU-Activity Short Name | (*)Start | (*)Finish | Original Duration(h) | (*)Actual Duration(h) | GWDXAG-Asset | GWDXAG-Rig Name | GWDXAG-Region | GWDXAG-Well Type | GWDXAG-Rig Activity Type | GWDXAG-Estimate
Completed | P50 | Rig Intake and Start up | RIG INTAKE | 2025-03-03 | 2025-04-02 | 19 | 30 | GOM.Region | EXP.Transocean Invictus | GOM | X | RSU | Mean
Completed | P50 | GC868-2 MD611 (SWX7) TOP HOLE DRL | SWX7 | 2025-04-02 | 2025-04-12 | 10 | 10 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Mean
Completed | P50 | GC868-3 (SWX8) TOP HOLE DRL | SWX8 | 2025-04-12 | 2025-04-21 | 10 | 9 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Mean
Completed | P50 | GC868-1 (SWX4) ST DRL | MD612 (SWX4) ST D | 2025-04-21 | 2025-05-29 | 38 | 38 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Mean
Completed | P50 | GC868-1 (SWX4) CPL | MD612 (SWX4) C | 2025-05-29 | 2025-07-21 | 62 | 53 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Mean
In Progress | P50 | GC868-2 MD611 (SWX7) DRL | MD611 (SWX7) D | 2025-07-21 | 2025-09-25 | 66 | 0 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Mean
Not Started | P50 | WOW |  | 2025-09-25 | 2025-10-25 | 30 | 0 | GOM.Region | EXP.Transocean Invictus | GOM | X | WOW | Mean
Not Started | P50 | GC868-2 MD611 (SWX7) CPL | MD611 (SWX7) C | 2025-10-25 | 2025-12-14 | 50 | 0 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Mean
Not Started | P50 | GC868-3 (SWX8) DRL | GC868-3 (SWX8) D | 2025-12-14 | 2026-02-07 | 55 | 0 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Mean
Not Started | P50 | GC868-3 (SWX8) CPL | GC868-3 (SWX8) C | 2026-02-07 | 2026-03-29 | 50 | 0 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Mean
Not Started | P50 | WEST BUMP APPRAISAL DRL | WEST BUMP D | 2026-03-29 | 2026-10-02 | 187 | 0 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Mean
Not Started | P50 | WOW |  | 2026-10-02 | 2026-11-01 | 30 | 0 | GOM.Region | EXP.Transocean Invictus | GOM | OTH | WOW | Mean
Not Started | P50 | Kaskida Batch Set (Paleogene) DRL | Kaskida B | 2026-11-01 | 2027-01-05 | 65 | 0 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Mean
Not Started | P50 | Kaskida (KA-112) DRL | KA-112 D | 2027-01-05 | 2027-04-29 | 114 | 0 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Mean
Not Started | P50 | Kaskida (KA-114) DRL | KA-114 D | 2027-04-29 | 2027-08-17 | 110 | 0 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Mean
Not Started | P50 | WOW |  | 2027-08-17 | 2027-09-16 | 30 | 0 | GOM.Region | EXP.Transocean Invictus | GOM | OTH | WOW | Mean
Not Started | P50 | Kaskida (KA-111) DRL | KA-111 D | 2027-09-16 | 2027-12-30 | 105 | 0 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Mean
Not Started | P50 | Kaskida (KA-214) (Paleogene) DRL | KA-214 D | 2027-12-30 | 2028-04-10 | 102 | 0 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Mean
Not Started | P50 | Kaskida (KA-212) (Paleogene) DRL | KA-212 D | 2028-04-10 | 2028-07-21 | 102 | 0 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Mean
Not Started | P50 | Kaskida (KA-211) (Paleogene) DRL | KA-211 D | 2028-07-21 | 2028-11-03 | 105 | 0 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Mean
Not Started | P50 | WOW |  | 2028-11-03 | 2028-12-03 | 30 | 0 | GOM.Region | EXP.Transocean Invictus | GOM | OTH | WOW | Mean
Not Started | P50 | Brazos DRL | Brazos D | 2028-12-03 | 2029-04-16 | 134 | 0 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Mean
Not Started | P50 | Garibaldi DRL | Garibaldi D | 2029-04-16 | 2029-08-28 | 134 | 0 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Mean
Not Started | P50 | WOW |  | 2029-08-28 | 2029-09-27 | 30 | 0 | GOM.Region | EXP.Transocean Invictus | GOM | OTH | WOW | Mean
Not Started | P50 | White Space | WS | 2029-09-27 | 2030-05-01 | 216 | 0 | GOM.Region | EXP.Transocean Invictus | GOM | X | WS | Mean
Not Started | P50 | RIG INTAKE | RIG INTAKE | 2028-01-20 | 2028-02-29 | 40 | 0 | GOM.Kaskida | GOM.Atlas | GOM | X | RSU | Mean
Not Started | P50 | Kaskida (KA-112) (Paleogene) CPL | KA-112 C | 2028-02-29 | 2028-05-14 | 75 | 0 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | Kaskida (KA-114) (Paleogene) CPL | KA-114 C | 2028-05-14 | 2028-07-25 | 72 | 0 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | Kaskida (KA-111) (Paleogene) CPL | KA-111 C | 2028-07-25 | 2028-10-02 | 69 | 0 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | WOW |  | 2028-10-02 | 2028-11-01 | 30 | 0 | GOM.Kaskida | GOM.Atlas | GOM | OTH | WOW | Mean
Not Started | P50 | White Space | WS | 2028-11-01 | 2028-11-03 | 2 | 0 | GOM.Region | GOM.Atlas | GOM | X | WS | Mean
Not Started | P50 | Kaskida (KA-214) (Paleogene) CPL | KA-214 C | 2028-11-03 | 2029-01-09 | 67 | 0 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | Kaskida (KA-212) (Paleogene) CPL | KA-212 C | 2029-01-09 | 2029-03-17 | 67 | 0 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | Kaskida (KA-211) (Paleogene) CPL | KA-211 C | 2029-03-17 | 2029-05-23 | 67 | 0 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | Tiber (TI-212) (Paleogene) CPL | TI-212 C | 2029-05-23 | 2029-07-14 | 52 | 0 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | Tiber (TI-211) (Paleogene) CPL | TI-211 C | 2029-07-14 | 2029-09-04 | 52 | 0 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | WOW |  | 2029-09-04 | 2029-10-04 | 30 | 0 | GOM.Kaskida | GOM.Atlas | GOM | OTH | WOW | Mean
Not Started | P50 | Tiber (TI-111) (Paleogene) CPL | TI-111 C | 2029-10-04 | 2029-11-25 | 52 | 0 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Mean
Not Started | P50 | Tiber (TI-113) (Paleogene) CPL | TI-113 C | 2029-11-25 | 2030-01-16 | 52 | 0 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Mean
Completed | P50 | Penguin BWM |  | 2025-03-25 | 2025-03-27 | 4 | 2 | GOM.GOMX | GOM.Black Hornet | GOM | X | RM | Mean
In Progress | P50 | Penguin DRL | Penguin D | 2025-03-27 | 2025-08-11 | 113 | 66 | GOM.GOMX | GOM.Black Hornet | GOM | MPP | DRL | Mean
Not Started | P50 | ATL DC153 DRL | DC153 D | 2025-08-11 | 2025-08-23 | 12 | 0 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | DRL | Mean
Not Started | P50 | DC104 WI CPL | DC104 WI C | 2025-08-23 | 2025-10-11 | 49 | 0 | GOM.Atlantis | GOM.Black Hornet | GOM | MPI | CPL | Mean
Not Started | P50 | WOW |  | 2025-10-11 | 2025-11-10 | 30 | 0 | GOM.Region | GOM.Black Hornet | GOM | OTH | WOW | Mean
Not Started | P50 | ATL DC153 DRL | DC153 D | 2025-11-10 | 2026-02-01 | 83 | 0 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | DRL | Mean
Not Started | P50 | ATL DC153 CPL | DC153 C | 2026-02-01 | 2026-03-20 | 47 | 0 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | CPL | Mean
Not Started | P50 | BWM 10 Year Rig Maintenance |  | 2026-03-20 | 2026-03-27 | 7 | 0 | GOM.Region | GOM.Black Hornet | GOM | X | RM | Mean
Not Started | P50 | BWM |  | 2026-03-27 | 2026-03-31 | 4 | 0 | GOM.Nakika | GOM.Black Hornet | GOM | X | RM | Mean
Not Started | P50 | Fourier F7 DRL | F7 D | 2026-03-31 | 2026-05-06 | 36 | 0 | GOM.Nakika | GOM.Black Hornet | GOM | DVP | DRL | Mean
Not Started | P50 | Fourier F7 CPL | F7 C | 2026-05-06 | 2026-06-08 | 33 | 0 | GOM.Nakika | GOM.Black Hornet | GOM | DVP | CPL | Mean
Not Started | P50 | Conifer DRL | Conifer D | 2026-06-08 | 2026-10-20 | 134 | 0 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Mean
Not Started | P50 | WOW |  | 2026-10-20 | 2026-11-19 | 30 | 0 | GOM.Region | GOM.Black Hornet | GOM | OTH | WOW | Mean
Not Started | P50 | NBr2 DRL | NBr2 D | 2026-11-19 | 2027-03-24 | 125 | 0 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | DRL | Mean
Not Started | P50 | NBr2 CPL | NBr2 C | 2027-03-24 | 2027-05-13 | 50 | 0 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | CPL | Mean
Not Started | P50 | Mazama DRL | Mazama D | 2027-05-13 | 2027-09-07 | 117 | 0 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Mean
Not Started | P50 | WOW |  | 2027-09-07 | 2027-10-07 | 30 | 0 | GOM.Region | GOM.Black Hornet | GOM | X | WOW | Mean
Not Started | P50 | RAPID CREEK DRL | RAPID CREEK D | 2027-10-07 | 2028-03-02 | 147 | 0 | GOM.GOMX | GOM.Black Hornet | GOM | MPP | DRL | Mean
Not Started | P50 | Duchess DRL | Duchess D | 2028-03-02 | 2028-06-20 | 110 | 0 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Mean
Not Started | P50 | Tiber (T1-212) (Paleogene) DRL | T1-212 D | 2028-06-20 | 2028-10-13 | 115 | 0 | GOM.Tiber | GOM.Black Hornet | GOM | MPP | DRL | Mean
Not Started | P50 | WOW |  | 2028-10-13 | 2028-11-12 | 30 | 0 | GOM.Region | GOM.Black Hornet | GOM | X | WOW | Mean
Not Started | P50 | Tiber (T1-211) (Paleogene) DRL | T1-211 D | 2028-11-12 | 2029-03-03 | 111 | 0 | GOM.Tiber | GOM.Black Hornet | GOM | MPP | DRL | Mean
Not Started | P50 | Tiber (T1-111) (Paleogene) DRL | T1-111 D | 2029-03-03 | 2029-06-18 | 107 | 0 | GOM.Tiber | GOM.Black Hornet | GOM | MPP | DRL | Mean
Not Started | P50 | Tiber (T1-113) (Paleogene) DRL | T1-113 D | 2029-06-18 | 2029-09-30 | 104 | 0 | GOM.Tiber | GOM.Black Hornet | GOM | EXP | DRL | Mean
Not Started | P50 | WOW |  | 2029-09-30 | 2029-10-30 | 30 | 0 | GOM.Region | GOM.Black Hornet | GOM | X | WOW | Mean
Not Started | P50 | KC010 - Guadalupe 1 (Paleogene) DRL | Guadalupe1 D | 2029-10-30 | 2030-03-02 | 123 | 0 | GOM.Paleogene | GOM.Black Hornet | GOM | DVP | DRL | Mean
Completed | P50 | GC825-MD424 (Si6) CPL | MD424-Si6 C | 2025-02-05 | 2025-05-11 | 59 | 95 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Completed | P50 | BWM & 5yr bop recert |  | 2025-05-11 | 2025-05-25 | 14 | 14 | GOM.Region | GOM.Black Lion | GOM | X | RM | Mean
In Progress | P50 | MD122 (SP3) DRL | MD122 (SP3) D | 2025-05-25 | 2025-07-30 | 49 | 7 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | MD122 (SP3) CPL | MD122 (SP3) C | 2025-07-30 | 2025-09-18 | 50 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Not Started | P50 | WOW |  | 2025-09-18 | 2025-10-18 | 30 | 0 | GOM.Region | GOM.Black Lion | GOM | OTH | WOW | Mean
Not Started | P50 | NPi22 DRL | NPi22 D | 2025-10-18 | 2025-12-27 | 70 | 0 | GOM.Thunder Horse | GOM.Black Lion | GOM | MPP | DRL | Mean
Not Started | P50 | NPi22 CPL | NPi22 C | 2025-12-27 | 2026-02-15 | 50 | 0 | GOM.Thunder Horse | GOM.Black Lion | GOM | MPP | CPL | Mean
Not Started | P50 | MD222 SP4 DRL | MD222 SP4 D | 2026-02-15 | 2026-04-24 | 68 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Mean
Not Started | P50 | MD222 SP4 CPL | MD222 SP4 C | 2026-04-24 | 2026-06-13 | 50 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Mean
Not Started | P50 | Batch set MD411 / MD423 DRL | MD B | 2026-06-13 | 2026-06-23 | 10 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | MD423 DRL | MD423 D | 2026-06-23 | 2026-08-21 | 59 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | MD423 CPL | MD423 C | 2026-08-21 | 2026-10-10 | 50 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Not Started | P50 | WOW |  | 2026-10-10 | 2026-11-09 | 30 | 0 | GOM.Region | GOM.Black Lion | GOM | X | WOW | Mean
Not Started | P50 | GC825-MD411 (SI10) DRL | MD411 (SI10) D | 2026-11-09 | 2027-01-15 | 67 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | GC825-MD411 (SI10) CPL | MD411 (SI10) C | 2027-01-15 | 2027-03-15 | 59 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Not Started | P50 | BWM 10 yr Rig Maintenance |  | 2027-03-15 | 2027-03-22 | 7 | 0 | GOM.Region | GOM.Black Lion | GOM | X | RM | Mean
Not Started | P50 | Argos #14 SWP3 DRL | Argos #14 SWP3 D | 2027-03-22 | 2027-06-02 | 72 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Mean
Not Started | P50 | MD Paleogene DRL | MD Paleogene D | 2027-06-02 | 2027-07-03 | 31 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Mean
Not Started | P50 | Argos #14 SWP3 CPL | Argos #14 SWP3 C | 2027-07-03 | 2027-08-22 | 50 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Mean
Not Started | P50 | WOW |  | 2027-08-22 | 2027-09-21 | 30 | 0 | GOM.Region | GOM.Black Lion | GOM | OTH | WOW | Mean
Not Started | P50 | Si7 DRL | Si7 D | 2027-09-21 | 2027-12-02 | 72 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | Si7 CPL | Si7 C | 2027-12-02 | 2028-01-30 | 59 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Not Started | P50 | GC825-x MD412 (SI9) ST DRL | MD412 (SI9) D-ST | 2028-01-30 | 2028-04-11 | 72 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | GC825-x MD412 (SI9) CPL | MD412 (SI9) C | 2028-04-11 | 2028-06-09 | 59 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Not Started | P50 | Argos SWX INFIL PH1 DRL | ASWX NFIL 1 D | 2028-06-09 | 2028-08-13 | 65 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | Argos SWX INFIL PH1 CPL | ASWX NFIL 1 C | 2028-08-13 | 2028-10-02 | 50 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Not Started | P50 | WOW |  | 2028-10-02 | 2028-11-01 | 30 | 0 | GOM.Region | GOM.Black Lion | GOM | OTH | WOW | Mean
Not Started | P50 | Argos SWX INFIL PH2 DRL | ASWX NFIL 2 D | 2028-11-01 | 2029-01-05 | 65 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | Argos SWX INFIL PH2 CPL | ASWX NFIL 2 C | 2029-01-05 | 2029-02-24 | 50 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Not Started | P50 | ARGOS INFILL 1 DRL | ARG INFL 1 D | 2029-02-24 | 2029-05-07 | 72 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Mean
Not Started | P50 | ARGOS INFILL 1 CPL | ARG INFL 1 C | 2029-05-07 | 2029-06-26 | 50 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Mean
Not Started | P50 | ARGOS INFILL WI 1 DRL | ARG INFL WI 1 D | 2029-06-26 | 2029-09-06 | 72 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Mean
Not Started | P50 | WOW |  | 2029-09-06 | 2029-10-06 | 30 | 0 | GOM.Region | GOM.Black Lion | GOM | OTH | WOW | Mean
Not Started | P50 | ARGOS INFILL WI 1 CPL | ARG INFL WI 1 C | 2029-10-06 | 2029-12-04 | 59 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Mean
Not Started | P50 | ARGOS INFILL 2 DRL | ARG INFL 2 D | 2029-12-04 | 2030-02-14 | 72 | 0 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Mean
Completed | P50 | DC123 Decomp PA | DC123 PA | 2025-01-01 | 2025-02-08 | 30 | 38 | GOM.Atlantis | GOM.Ice Max | GOM | DVP | P&A | Mean
Completed | P50 | DC123 ST DRL | DC123 ST D | 2025-02-08 | 2025-04-18 | 41 | 69 | GOM.Atlantis | GOM.Ice Max | GOM | DVP | DRL | Mean
Completed | P50 | DC123 ST CPL | DC123 C | 2025-04-18 | 2025-05-24 | 32 | 36 | GOM.Atlantis | GOM.Ice Max | GOM | DVP | CPL | Mean
In Progress | P50 | DC104 WI DRL | DC104 WI D | 2025-05-24 | 2025-08-15 | 56 | 8 | GOM.Atlantis | GOM.Ice Max | GOM | MPI | DRL | Mean
Not Started | P50 | MC777-4 PA | 777-4 PA | 2025-08-15 | 2025-10-23 | 69 | 0 | GOM.Thunder Horse | GOM.Ice Max | GOM | WW | P&A | Mean
Not Started | P50 | Demob | DM | 2025-10-23 | 2025-10-30 | 7 | 0 | GOM.Region | GOM.Ice Max | GOM | X | MOB | Mean
Completed | P50 | DC311 (RLWI) INTERV | DC311 | 2025-01-03 | 2025-01-23 | 24 | 20 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Mean
Completed | P50 | DC131 (RLWI) INTERV | DC131 | 2025-01-23 | 2025-02-07 | 20 | 15 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Mean
Completed | P50 | DC122 (RLWI) INTERV | DC122 | 2025-02-07 | 2025-02-09 | 2 | 2 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Mean
Completed | P50 | DC111 (RLWI) INTERV | DC111 | 2025-02-09 | 2025-02-13 | 4 | 4 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Mean
Completed | P50 | DC133 (RLWI) INTERV | DC133 | 2025-02-13 | 2025-02-17 | 4 | 4 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Mean
Completed | P50 | Thunder Horse Pumping | TH Pump | 2025-02-17 | 2025-03-25 | 57 | 36 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Mean
Completed | P50 | A7 GL INTERV | A7 GL IV | 2025-02-01 | 2025-02-21 | 41 | 20 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Mean
In Progress | P50 | MD17 (M20) CPL | MD17 (M20) C | 2025-04-20 | 2025-09-09 | 135 | 42 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Mean
Not Started | P50 | Rig Maintenance C3 | C3 | 2025-09-09 | 2025-09-12 | 3 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Mean
Not Started | P50 | WOW |  | 2025-09-12 | 2025-10-22 | 40 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | WOW | Mean
Not Started | P50 | White Space | WS | 2025-10-22 | 2025-11-23 | 32 | 0 | GOM.Region | GOM.Mad Dog SPAR | GOM | X | WS | Mean
Not Started | P50 | A10 WL INTERV | A10 WL IV | 2025-11-23 | 2025-12-02 | 9 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Mean
Not Started | P50 | A5 WH Seal Repair INTERV | A5 IV | 2025-12-01 | 2025-12-08 | 7 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | P50 | MD15 (A13) DRL | MD15 (A13) D | 2025-12-02 | 2026-06-17 | 197 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Mean
Not Started | P50 | A10 Pump INTERV | A10 P IV | 2026-02-28 | 2026-03-22 | 22 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Mean
Not Started | P50 | WOW |  | 2026-06-17 | 2026-07-27 | 40 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | WOW | Mean
Not Started | P50 | MD15 (A13) CPL | MD15 (A13) C | 2026-07-27 | 2026-12-17 | 143 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Mean
Not Started | P50 | MD14 New Top Hole DRL | MD14 New Top Hole D | 2026-12-17 | 2027-05-16 | 150 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Mean
Not Started | P50 | TBD WSO pump & WL PH INTERV | WSO & WL PH IV | 2027-05-10 | 2027-06-09 | 30 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Mean
Not Started | P50 | MAD DOG TAR | TAR | 2027-05-16 | 2027-06-17 | 32 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Mean
Not Started | P50 | MD14 New Top Hole DRL | MD14 New Top Hole D | 2027-06-17 | 2027-09-01 | 76 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Mean
Not Started | P50 | WOW |  | 2027-09-01 | 2027-10-11 | 40 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | WOW | Mean
Not Started | P50 | MD14 New Top HoleCPL | MD14 New Top Hole C | 2027-10-11 | 2028-02-15 | 127 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Mean
Not Started | P50 | GC782-8 A-6 ST De-CPL | A-6 ST De-C | 2028-02-15 | 2028-04-05 | 50 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Mean
Not Started | P50 | TBD WSO pump & WL PH INTERV | WSO & WL PH IV | 2028-03-10 | 2028-04-09 | 30 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Mean
Not Started | P50 | GC782-8 A-6 ST-DRL | A-6 ST-D | 2028-04-05 | 2028-06-06 | 62 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Mean
Not Started | P50 | GC782-8 A-6 ST CPL | A-6 ST C | 2028-06-06 | 2028-09-30 | 116 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Mean
Not Started | P50 | WOW |  | 2028-09-30 | 2028-11-09 | 40 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | WOW | Mean
Not Started | P50 | MD14 (A13) P&A | MD14 (A13) PA | 2028-11-09 | 2028-12-24 | 45 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | P&A | Mean
Not Started | P50 | Rig Maintenance |  | 2028-12-24 | 2029-01-07 | 14 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Mean
Not Started | P50 | TBD WSO pump & WL PH INTERV | WSO & WL PH IV | 2029-01-04 | 2029-02-03 | 30 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Mean
Not Started | P50 | GC782--7 A-4 ST-DRL | A-4 ST-D | 2029-01-07 | 2029-04-29 | 112 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Mean
Not Started | P50 | GC782--7 A-4 CPL | A-4 C | 2029-04-29 | 2029-07-23 | 85 | 0 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Mean
Completed | P50 | BWM (laying out BOP and picking up CWOR) |  | 2025-01-17 | 2025-01-24 | 7 | 7 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Completed | P50 | BWM (CWOR deck test) |  | 2025-01-24 | 2025-02-20 | 27 | 27 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Completed | P50 | MC778-2 (PDQ) INTERV | 778-2 Iv | 2025-02-20 | 2025-03-26 | 28 | 34 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Mean
Completed | P50 | MC822-4 (PDQ) INTERV | 822-4 Iv | 2025-03-26 | 2025-04-06 | 23 | 11 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Mean
Completed | P50 | MC822-7 (PDQ) INTERV | 822-7 Iv | 2025-04-06 | 2025-04-18 | 19 | 12 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Mean
In Progress | P50 | BWM Rig Maintenance |  | 2025-04-18 | 2025-09-28 | 147 | 44 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | MC778-8 PXA Open Water Work (PDQ) INTERV | 778--8 PA | 2025-09-28 | 2025-10-07 | 9 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | P&A | Mean
Not Started | P50 | SPi7/8 DRL (PDQ) | SPi7/8 D | 2025-10-07 | 2026-03-01 | 145 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | MPI | DRL | Mean
Not Started | P50 | TAR | TAR | 2026-03-01 | 2026-05-19 | 79 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | WOW | Mean
Not Started | P50 | SPi7/8 CPL (PDQ) | SPi7/8 C | 2026-05-19 | 2026-08-26 | 99 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | MPI | CPL | Mean
Not Started | P50 | WOW |  | 2026-08-26 | 2026-09-25 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | WOW | Mean
Not Started | P50 | BWM Rig Maintenance |  | 2026-09-25 | 2026-10-25 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | BWM (laying out BOP and picking up CWOR) |  | 2026-10-25 | 2026-11-03 | 9 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | BWM (CWOR deck test) |  | 2026-11-03 | 2026-11-24 | 21 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | TH INTERV TBD 3 (PDQ) | PDQ Iv TBD3 | 2026-11-24 | 2026-12-24 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Mean
Not Started | P50 | TH INTERV TBD 4 (PDQ) | PDQ Iv TBD4 | 2026-12-24 | 2027-01-23 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Mean
Not Started | P50 | WOW |  | 2027-01-23 | 2027-02-17 | 25 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | WOW | Mean
Not Started | P50 | MC822-4 PXA (PDQ) INTERV | 822-4 PA | 2027-02-17 | 2027-04-28 | 70 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | P&A | Mean
Not Started | P50 | SPi11/6 DRL (PDQ) | SPi11/6 D | 2027-04-28 | 2027-10-06 | 161 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | MPI | DRL | Mean
Not Started | P50 | WOW |  | 2027-10-06 | 2027-11-05 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | WOW | Mean
Not Started | P50 | SPi11/6 CPL (PDQ) | SPi11/6 C | 2027-11-05 | 2028-02-17 | 104 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | MPI | CPL | Mean
Not Started | P50 | BWM Rig Maintenance |  | 2028-02-17 | 2028-03-18 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | WOW |  | 2028-03-18 | 2028-04-12 | 25 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | WOW | Mean
Not Started | P50 | BWM (laying out BOP and picking up CWOR) |  | 2028-04-12 | 2028-04-21 | 9 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | BWM |  | 2028-04-21 | 2028-05-12 | 21 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | TH INTERV TBD 5 (PDQ) | PDQ Iv TBD5 | 2028-05-12 | 2028-06-11 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Mean
Not Started | P50 | TH INTERV TBD 6 (PDQ) | PDQ Iv TBD6 | 2028-06-11 | 2028-07-11 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Mean
Not Started | P50 | BWM |  | 2028-07-11 | 2028-08-10 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | WOW |  | 2028-08-10 | 2028-09-09 | 30 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | WOW | Mean
Not Started | P50 | SPi4/5w DRL | SPi4/5w D | 2028-09-09 | 2029-02-17 | 161 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | MPI | DRL | Mean
Not Started | P50 | WOW |  | 2029-02-17 | 2029-03-14 | 25 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | WOW | Mean
Not Started | P50 | SPi4/5w CPL | SPi4/5w C | 2029-03-14 | 2029-06-26 | 104 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | MPI | CPL | Mean
Not Started | P50 | SPi4/5w Rig Injection Test CPL | RIT | 2029-06-26 | 2029-07-06 | 10 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | MPI | CPL | Mean
Not Started | P50 | BWM RIG MAINTENANCE |  | 2029-07-06 | 2029-10-04 | 90 | 0 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Mean
Not Started | P50 | Rig Start up | RSU | 2025-11-25 | 2025-12-05 | 10 | 0 | GOM.Region | GOM.Q5000 | GOM | WW | RSU | Mean
Not Started | P50 | MC822-3 (RLWI) INTERV | 822-3 | 2025-12-05 | 2026-01-01 | 27 | 0 | GOM.Thunder Horse | GOM.Q5000 | GOM | WW | WWP | Mean
Not Started | P50 | Thunder Horse P45 C/O | TH P45 | 2026-01-01 | 2026-01-20 | 19 | 0 | GOM.Thunder Horse | GOM.Q5000 | GOM | WW | WWP | Mean
Completed | P50 | Exp |  |  | 2021-02-02 | 0 | 0 | GOM.Region | GOM.Q5000 | GOM | OTH | IAC | Mean
Not Started | P50 | Rig Start up | RSU | 2026-01-01 | 2026-01-11 | 10 | 0 | GOM.Region | GOM.TBD #02 | GOM | WW | RSU | Mean
Not Started | P50 | Restoration Place Holder INTERV | PH IV | 2026-01-11 | 2026-02-15 | 35 | 0 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Mean
Not Started | P50 | White Space | WS | 2026-02-15 | 2027-01-01 | 320 | 0 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Mean
Not Started | P50 | Restoration Place Holder INTERV | PH IV | 2027-01-01 | 2027-06-30 | 180 | 0 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Mean
Not Started | P50 | White Space | WS | 2027-06-30 | 2028-01-01 | 185 | 0 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Mean
Not Started | P50 | Restoration Place Holder INTERV | PH IV | 2028-01-01 | 2028-06-29 | 180 | 0 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Mean
Not Started | P50 | White Space | WS | 2028-06-29 | 2029-01-01 | 186 | 0 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Mean
Not Started | P50 | Restoration Place Holder INTERV | PH IV | 2029-01-01 | 2029-06-30 | 180 | 0 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Mean
Not Started | P50 | Rig Start up | RSU | 2026-04-01 | 2026-05-20 | 49 | 0 | GOM.Region | GOM.TBD #07 | GOM | WW | RSU | Mean
Not Started | P50 | DC105 (MFXB75) DRL | DC105 (MFXB75) D | 2026-05-20 | 2026-07-19 | 60 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | MPP | DRL | Mean
Not Started | P50 | DC105 (MFXB75) CPL | DC105 (MFXB75) C | 2026-07-19 | 2026-09-07 | 50 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | MPP | CPL | Mean
Not Started | P50 | WOW |  | 2026-09-07 | 2026-10-07 | 30 | 0 | GOM.Region | GOM.TBD #07 | GOM | OTH | WOW | Mean
Not Started | P50 | ATL DC152 DRL | DC152 D | 2026-10-07 | 2026-12-02 | 56 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Mean
Not Started | P50 | ATL DC152 CPL | DC152 C | 2026-12-02 | 2027-01-12 | 41 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Mean
Not Started | P50 | DC106 (MFXN54) DRL | DC106 (MFXN54) D | 2027-01-12 | 2027-03-07 | 54 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | DRL | Mean
Not Started | P50 | DC106 (MFXN54) CPL | DC106 (MFXN54) C | 2027-03-07 | 2027-04-25 | 49 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | CPL | Mean
Not Started | P50 | DC123 RE-CPL | DC123 RE-C | 2027-04-25 | 2027-06-24 | 60 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Mean
Not Started | P50 | Isabela 1 (I-1) PA | I-1 PA | 2027-06-24 | 2027-09-02 | 70 | 0 | GOM.Nakika | GOM.TBD #07 | GOM | WW | P&A | Mean
Not Started | P50 | WOW |  | 2027-09-02 | 2027-10-02 | 30 | 0 | GOM.Region | GOM.TBD #07 | GOM | OTH | WOW | Mean
Not Started | P50 | NBr7 DRL | NBr7 D | 2027-10-02 | 2028-02-04 | 125 | 0 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | DRL | Mean
Not Started | P50 | NBr7 CPL | NBr7 C | 2028-02-04 | 2028-03-25 | 50 | 0 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | CPL | Mean
Not Started | P50 | EXPLORATION PH8 DRL | EXP PH8 D | 2028-03-25 | 2028-07-21 | 118 | 0 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Mean
Not Started | P50 | ATL ST PH DRL #1 | ATL ST PH1 D | 2028-07-21 | 2028-09-18 | 59 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Mean
Not Started | P50 | ATL ATL ST PH CPL #1 | ATL ST PH1 C | 2028-09-18 | 2028-10-18 | 30 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Mean
Not Started | P50 | WOW |  | 2028-10-18 | 2028-11-17 | 30 | 0 | GOM.Region | GOM.TBD #07 | GOM | OTH | WOW | Mean
Not Started | P50 | ATL ST PH DRL #2 | ATL ST PH2 D | 2028-11-17 | 2029-01-16 | 60 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Mean
Not Started | P50 | ATL ATL ST PH CPL #2 | ATL ST PH2 C | 2029-01-16 | 2029-02-15 | 30 | 0 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Mean
Not Started | P50 | NPi18 DRL | NPi18 D | 2029-02-15 | 2029-06-10 | 115 | 0 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | DRL | Mean
Not Started | P50 | NPi18 CPL | NPi18 C | 2029-06-10 | 2029-07-30 | 50 | 0 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | CPL | Mean
Not Started | P50 | MC775-3 (NPi13) PA | 775-3 PA | 2029-07-30 | 2029-08-29 | 30 | 0 | GOM.Thunder Horse | GOM.TBD #07 | GOM | WW | P&A | Mean
Not Started | P50 | WOW |  | 2029-08-29 | 2029-09-28 | 30 | 0 | GOM.Region | GOM.TBD #07 | GOM | OTH | WOW | Mean
Not Started | P50 | APOLLO DRL | APOLLO D | 2029-09-28 | 2030-01-16 | 110 | 0 | GOM.GOMX | GOM.TBD #07 | GOM | MPP | DRL | Mean