## EARLY CASE
Activity Status | (*)WBS Name | Activity Name | (*)Start | (*)Finish | Original Duration(h) | GWDXAG-Asset | GWDXAG-Rig Name | GWDXAG-Region | GWDXAG-Well Type | GWDXAG-Rig Activity Type | GWDXAG-Estimate
Completed | Early Case | Rig Intake and Start up | 2025-03-03 | 2025-04-02 | 12 | GOM.Region | EXP.Transocean Invictus | GOM | X | RSU | Early
Completed | Early Case | GC868-2 MD611 (SWX7) TOP HOLE DRL | 2025-04-02 | 2025-04-10 | 8 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Completed | Early Case | GC868-3 (SWX8) TOP HOLE DRL | 2025-04-10 | 2025-04-21 | 8 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Completed | Early Case | GC868-1 (SWX4) ST DRL | 2025-04-21 | 2025-05-29 | 34 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Completed | Early Case | GC868-1 (SWX4) CPL | 2025-05-29 | 2025-07-21 | 41 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Early
In Progress | Early Case | GC868-2 MD611 (SWX7) DRL | 2025-07-21 | 2025-09-06 | 47 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | GC868-2 MD611 (SWX7) CPL | 2025-09-06 | 2025-10-13 | 37 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Early
Not Started | Early Case | GC868-3 (SWX8) DRL | 2025-10-13 | 2025-11-24 | 42 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | GC868-3 (SWX8) CPL | 2025-11-24 | 2026-01-10 | 47 | GOM.Argos | EXP.Transocean Invictus | GOM | MPP | CPL | Early
Not Started | Early Case | WEST BUMP APPRAISAL DRL | 2026-01-10 | 2026-06-28 | 169 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida Batch Set (Paleogene) DRL | 2026-06-28 | 2026-08-21 | 54 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida (KA-112) (Paleogene) DRL | 2026-08-21 | 2026-11-20 | 91 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida (KA-114) (Paleogene) DRL | 2026-11-20 | 2027-02-20 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida (KA-111) (Paleogene) DRL | 2027-02-20 | 2027-05-23 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Kaskida (KA-214) (Paleogene) DRL | 2027-05-23 | 2027-08-23 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | Kaskida (KA-212) (Paleogene) DRL | 2027-08-23 | 2027-11-23 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | Kaskida (KA-211) (Paleogene) DRL | 2027-11-23 | 2028-02-23 | 92 | GOM.Kaskida | EXP.Transocean Invictus | GOM | MPP | DRL | Early
Not Started | Early Case | Brazos DRL | 2028-02-23 | 2028-06-23 | 121 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Garibaldi DRL | 2028-06-23 | 2028-10-22 | 121 | GOM.GOMX | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | White Space | 2028-10-22 | 2030-05-01 | 556 | GOM.Region | EXP.Transocean Invictus | GOM | X | WS | Early
Not Started | Early Case | WEST BUMP 1 DRL | 2030-05-01 | 2030-09-28 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | White Space | 2030-09-28 | 2031-05-10 | 224 | GOM.Region | EXP.Transocean Invictus | GOM | X | WS | Early
Not Started | Early Case | WEST BUMP 2 DRL | 2031-05-10 | 2031-10-07 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Gila 1 DRL | 2031-10-07 | 2032-03-05 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Gila 2 DRL | 2032-03-05 | 2032-08-02 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Gila 3 DRL | 2032-08-02 | 2032-12-30 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Conifer 3 DRL | 2032-12-30 | 2033-05-29 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Conifer 4 DRL | 2033-05-29 | 2033-10-26 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | WEST BUMP 3 DRL | 2033-10-26 | 2033-12-25 | 60 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | White Space | 2033-12-25 | 2035-02-01 | 403 | GOM.Region | EXP.Transocean Invictus | GOM | X | WS | Early
Not Started | Early Case | Gibson 1 DRL | 2035-02-01 | 2035-07-01 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Gibson 2 DRL | 2035-07-01 | 2035-11-28 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | Conifer 5 DRL | 2035-11-28 | 2036-04-26 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | West Bump 4 DRL | 2036-04-26 | 2036-09-23 | 150 | GOM.Paleogene | EXP.Transocean Invictus | GOM | EXP | DRL | Early
Not Started | Early Case | RIG INTAKE | 2028-01-20 | 2028-02-29 | 40 | GOM.Kaskida | GOM.Atlas | GOM | X | RSU | Early
Not Started | Early Case | Kaskida (KA-112) (Paleogene) CPL | 2028-02-29 | 2028-04-27 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-114) (Paleogene) CPL | 2028-04-27 | 2028-06-24 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-111) (Paleogene) CPL | 2028-06-24 | 2028-08-21 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-214) (Paleogene) CPL | 2028-08-21 | 2028-10-18 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-212) (Paleogene) CPL | 2028-10-18 | 2028-12-15 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Kaskida (KA-211) (Paleogene) CPL | 2028-12-15 | 2029-02-11 | 58 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-212) (Paleogene) CPL | 2029-02-11 | 2029-03-23 | 40 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-211) (Paleogene) CPL | 2029-03-23 | 2029-05-02 | 40 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-111) (Paleogene) CPL | 2029-05-02 | 2029-06-11 | 40 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-113) (Paleogene) CPL | 2029-06-11 | 2029-07-21 | 40 | GOM.Tiber | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | KC010 - Guadalupe 1 (Paleogene) CPL | 2029-07-21 | 2029-09-04 | 45 | GOM.Kaskida | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | KC010 - Guadalupe 2 (Paleogene) CPL | 2029-09-04 | 2029-10-19 | 45 | GOM.Kaskida | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2029-10-19 | 2029-11-13 | 25 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Tiber (TI-213) (Paleogene) CPL | 2029-11-13 | 2029-12-23 | 40 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | Tiber (TI-214) (Paleogene) CPL | 2029-12-23 | 2030-02-01 | 40 | GOM.Kaskida | GOM.Atlas | GOM | MPP | CPL | Early
Not Started | Early Case | White Space | 2030-02-01 | 2030-10-01 | 242 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | West Bump 1 CPL | 2030-10-01 | 2030-11-30 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2030-11-30 | 2031-10-07 | 311 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | West Bump 2 CPL | 2031-10-07 | 2031-12-06 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2031-12-06 | 2032-07-01 | 208 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Conifer 1 CPL | 2032-07-01 | 2032-08-30 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Conifer 2 CPL | 2032-08-30 | 2032-10-29 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2032-10-29 | 2033-01-02 | 65 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Gila 1 CPL | 2033-01-02 | 2033-03-03 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Gila 2 CPL | 2033-03-03 | 2033-05-02 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Gila 3 CPL | 2033-05-02 | 2033-07-01 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2033-07-01 | 2033-10-28 | 119 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | West Bump 3 CPL | 2033-10-28 | 2033-12-27 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Conifer 3 CPL | 2033-12-27 | 2034-02-25 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Conifer 4 CPL | 2034-02-25 | 2034-04-26 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2034-04-26 | 2035-11-28 | 581 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Gibson 1 CPL | 2035-11-28 | 2036-01-27 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | Gibson 2 CPL | 2036-01-27 | 2036-03-27 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2036-03-27 | 2036-04-30 | 34 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | Conifer 5 CPL | 2036-04-30 | 2036-06-29 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2036-06-29 | 2036-09-28 | 91 | GOM.Region | GOM.Atlas | GOM | X | WS | Early
Not Started | Early Case | West Bump 4 CPL | 2036-09-28 | 2036-11-27 | 60 | GOM.Paleogene | GOM.Atlas | GOM | DVP | CPL | Early
Completed | Early Case | FAR SOUTH DRL | 2024-11-01 | 2025-03-25 | 75 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | Penguin BWM | 2025-03-25 | 2025-03-27 | 2 | GOM.GOMX | GOM.Black Hornet | GOM | X | RM | Early
In Progress | Early Case | Penguin DRL | 2025-03-27 | 2025-08-07 | 98 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | ATL DC153 DRL | 2025-08-07 | 2025-08-15 | 8 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | DC104 WI CPL | 2025-08-15 | 2025-09-19 | 35 | GOM.Atlantis | GOM.Black Hornet | GOM | DVI | CPL | Early
Not Started | Early Case | ATL DC153 DRL | 2025-09-19 | 2025-11-12 | 54 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | ATL DC153 CPL | 2025-11-12 | 2025-12-17 | 35 | GOM.Atlantis | GOM.Black Hornet | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2025-12-17 | 2026-01-01 | 15 | GOM.Region | GOM.Black Hornet | GOM | X | WS | Early
Not Started | Early Case | BWM | 2026-01-01 | 2026-01-04 | 3 | GOM.Nakika | GOM.Black Hornet | GOM | X | RM | Early
Not Started | Early Case | Fourier F7 DRL | 2026-01-04 | 2026-02-04 | 31 | GOM.Nakika | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | Fourier F7 CPL | 2026-02-04 | 2026-03-04 | 28 | GOM.Nakika | GOM.Black Hornet | GOM | DVP | CPL | Early
Not Started | Early Case | White Space | 2026-03-04 | 2026-04-01 | 28 | GOM.Region | GOM.Black Hornet | GOM | X | WS | Early
Not Started | Early Case | Conifer DRL | 2026-04-01 | 2026-07-31 | 121 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | NBr2 DRL | 2026-07-31 | 2026-11-18 | 110 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | DRL | Early
Not Started | Early Case | NBr2 CPL | 2026-11-18 | 2027-01-02 | 45 | GOM.Thunder Horse | GOM.Black Hornet | GOM | MPP | CPL | Early
Not Started | Early Case | Mazama DRL | 2027-01-02 | 2027-04-09 | 97 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | RAPID CREEK DRL | 2027-04-09 | 2027-08-21 | 134 | GOM.GOMX | GOM.Black Hornet | GOM | MPP | DRL | Early
Not Started | Early Case | Duchess DRL | 2027-08-21 | 2027-11-19 | 90 | GOM.GOMX | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | TIBER (T1-212) (Paleogene) DRL | 2027-11-19 | 2028-02-21 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-211) (Paleogene) DRL | 2028-02-21 | 2028-05-25 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-111) (Paleogene) DRL | 2028-05-25 | 2028-08-27 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-113) (Paleogene) DRL | 2028-08-27 | 2028-11-29 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | KC010 - Guadalupe 1 (Paleogene) DRL | 2028-11-29 | 2029-03-13 | 104 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | KC010 - Guadalupe 2 (Paleogene) DRL | 2029-03-13 | 2029-06-25 | 104 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-213) (Paleogene) DRL | 2029-06-25 | 2029-09-27 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | TIBER (T1-214) (Paleogene) DRL | 2029-09-27 | 2029-12-30 | 94 | GOM.Tiber | GOM.Black Hornet | GOM | DVP | DRL | Early
Not Started | Early Case | Conifer 1 DRL | 2031-08-01 | 2031-12-29 | 150 | GOM.Paleogene | GOM.Black Hornet | GOM | EXP | DRL | Early
Not Started | Early Case | Conifer 2 DRL | 2031-12-29 | 2032-05-27 | 150 | GOM.Paleogene | GOM.Black Hornet | GOM | EXP | DRL | Early
Completed | Early Case | GC825-MD424 (Si6) DRL | 2024-09-14 | 2025-02-05 | 45 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Completed | Early Case | GC825-MD424 (Si6) CPL | 2025-02-05 | 2025-05-11 | 49 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Completed | Early Case | BWM 5yr bop recert | 2025-05-11 | 2025-05-25 | 14 | GOM.Region | GOM.Black Lion | GOM | X | RM | Early
In Progress | Early Case | MD122 (SP3) DRL | 2025-05-25 | 2025-07-30 | 43 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | MD122 (SP3) CPL | 2025-07-30 | 2025-09-03 | 35 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | NPi22 DRL | 2025-09-03 | 2025-10-28 | 55 | GOM.Thunder Horse | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | NPi22 CPL | 2025-10-28 | 2025-12-14 | 47 | GOM.Thunder Horse | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | MD222 (SP4) DRL | 2025-12-14 | 2026-01-28 | 45 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | MD222 (SP4) CPL | 2026-01-28 | 2026-03-16 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Batch set MD411 / MD423 DRL | 2026-03-16 | 2026-03-24 | 8 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | MD423 DRL | 2026-03-24 | 2026-05-14 | 51 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | MD423 CPL | 2026-05-14 | 2026-06-28 | 45 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | MD411 (SI10) DRL | 2026-06-28 | 2026-08-26 | 59 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | MD411 (SI10) CPL | 2026-08-26 | 2026-10-07 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | Argos #14 SWP3 DRL | 2026-10-07 | 2026-12-09 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | MD Paleogene DRL | 2026-12-09 | 2026-12-31 | 22 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | Argos #14 SWP3 CPL | 2026-12-31 | 2027-02-16 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Si7 DRL | 2027-02-16 | 2027-04-20 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | Si7 CPL | 2027-04-20 | 2027-06-01 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | (SI9) DRL | 2027-06-01 | 2027-08-03 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | (SI9) CPL | 2027-08-03 | 2027-09-14 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | Argos SWX INFILL PH1 DRL | 2027-09-14 | 2027-11-03 | 50 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | Argos SWX INFILL PH1 CPL | 2027-11-03 | 2027-12-20 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Argos SWX INFILL PH2 DRL | 2027-12-20 | 2028-02-08 | 50 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | Argos SWX INFILL PH2 CPL | 2028-02-08 | 2028-03-26 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Argos INFILL 1 DRL | 2028-03-26 | 2028-05-28 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | Argos INFILL 1 CPL | 2028-05-28 | 2028-07-14 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | Argos WI INFILL 1 DRL | 2028-07-14 | 2028-09-15 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | Argos WI INFILL 1 CPL | 2028-09-15 | 2028-10-27 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | Argos INFILL 2 DRL | 2028-10-27 | 2028-12-29 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPP | DRL | Early
Not Started | Early Case | Argos INFILL 2 CPL | 2028-12-29 | 2029-02-14 | 47 | GOM.Argos | GOM.Black Lion | GOM | MPP | CPL | Early
Not Started | Early Case | MC383-4 Kepler 4 PA INTERV | 2029-02-14 | 2029-03-21 | 35 | GOM.Nakika | GOM.Black Lion | GOM | WW | P&A | Early
Not Started | Early Case | Kepler 2 (K-2) Zonal Isolation PA | 2029-03-21 | 2029-04-25 | 35 | GOM.Nakika | GOM.Black Lion | GOM | WW | P&A | Early
Not Started | Early Case | Manuel 1 (M-1) Zonal Isolation PA | 2029-04-25 | 2029-05-30 | 35 | GOM.Nakika | GOM.Black Lion | GOM | WW | P&A | Early
Not Started | Early Case | Fourier 2 (F-2) Zonal Isolation PA | 2029-05-30 | 2029-07-04 | 35 | GOM.Nakika | GOM.Black Lion | GOM | WW | P&A | Early
Not Started | Early Case | Argos WI INFILL 2 DRL | 2029-07-04 | 2029-09-05 | 63 | GOM.Argos | GOM.Black Lion | GOM | MPI | DRL | Early
Not Started | Early Case | Argos WI INFILL 2 CPL | 2029-09-05 | 2029-10-17 | 42 | GOM.Argos | GOM.Black Lion | GOM | MPI | CPL | Early
Not Started | Early Case | EXPLORATION PH 9 DRL | 2029-10-17 | 2030-01-15 | 90 | GOM.GOMX | GOM.Black Lion | GOM | EXP | DRL | Early
Completed | Early Case | DC112 INTERV | 2024-12-15 | 2025-01-01 | 17 | GOM.Atlantis | GOM.Ice Max | GOM | WW | WWP | Early
Completed | Early Case | DC123 Decomp PA | 2025-01-01 | 2025-02-08 | 24 | GOM.Atlantis | GOM.Ice Max | GOM | DVP | P&A | Early
Completed | Early Case | DC123 ST DRL | 2025-02-08 | 2025-04-18 | 12 | GOM.Atlantis | GOM.Ice Max | GOM | MPP | DRL | Early
Completed | Early Case | DC123 ST CPL | 2025-04-18 | 2025-05-24 | 23 | GOM.Atlantis | GOM.Ice Max | GOM | DVP | CPL | Early
In Progress | Early Case | DC104 WI DRL | 2025-05-24 | 2025-08-09 | 38 | GOM.Atlantis | GOM.Ice Max | GOM | DVI | DRL | Early
Not Started | Early Case | MC777-4 PA | 2025-08-09 | 2025-09-25 | 47 | GOM.Thunder Horse | GOM.Ice Max | GOM | WW | P&A | Early
Not Started | Early Case | White Space | 2025-09-25 | 2025-09-29 | 4 | GOM.Region | GOM.Ice Max | GOM | X | WS | Early
Not Started | Early Case | Demob | 2025-09-29 | 2025-10-06 | 7 | GOM.Region | GOM.Ice Max | GOM | X | MOB | Early
Completed | Early Case | DC214 (RLWI) INTERV | 2024-12-15 | 2025-01-03 | 16 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC311 (RLWI) INTERV | 2025-01-03 | 2025-01-18 | 18 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | TH T41 Flushing(RLWI) INTERV | 2025-01-18 | 2025-01-23 | 5 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC131 (RLWI) INTERV | 2025-01-23 | 2025-02-07 | 15 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC122 (RLWI) INTERV | 2025-02-07 | 2025-02-09 | 2 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC111 (RLWI) INTERV | 2025-02-09 | 2025-02-10 | 3 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | DC133 BWM (RLWI) INTERV | 2025-02-10 | 2025-02-13 | 4 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | X | RM | Early
Completed | Early Case | DC133 (RLWI) INTERV | 2025-02-13 | 2025-02-17 | 4 | GOM.Atlantis | GOM.LWI.ISLVEN | GOM | WW | WWP | Early
Completed | Early Case | Thunder Horse Pumping | 2025-02-17 | 2025-03-25 | 30 | GOM.Thunder Horse | GOM.LWI.ISLVEN | GOM | WW | RM | Early
Completed | Early Case | MD17 (M20) DRL | 2024-11-23 | 2025-04-20 | 153 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Completed | Early Case | A7 GL | 2025-02-01 | 2025-02-21 | 33 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
In Progress | Early Case | MD17 (M20) CPL | 2025-04-20 | 2025-08-27 | 92 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | Rig Maintenance C3 | 2025-08-27 | 2025-08-30 | 3 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Not Started | Early Case | White Space | 2025-08-30 | 2025-11-22 | 84 | GOM.Region | GOM.Mad Dog SPAR | GOM | X | WS | Early
Not Started | Early Case | A10 WL INTERV | 2025-11-22 | 2025-12-01 | 9 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | MD15 (A13) DRL | 2025-12-01 | 2026-05-15 | 165 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Not Started | Early Case | A5 WH Seal Repair INTERV | 2025-12-01 | 2025-12-08 | 7 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | A10 Pump INTERV | 2026-02-28 | 2026-03-22 | 22 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | MD15 (A13) CPL | 2026-05-15 | 2026-08-16 | 93 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | MD14 New top hole DRL | 2026-08-16 | 2027-01-23 | 160 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Not Started | Early Case | MD14 New Top Hole CPL | 2027-01-23 | 2027-04-26 | 93 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | MAD DOG TAR | 2027-04-26 | 2027-05-28 | 32 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | OTH | TAR | Early
Not Started | Early Case | TBD WSO pump & WL PH INTERV | 2027-05-08 | 2027-06-07 | 30 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | GC782-8 A-6 ST De-CPL | 2027-05-28 | 2027-07-17 | 50 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | GC782-8 A-6 ST-DRL | 2027-07-17 | 2027-09-05 | 50 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Not Started | Early Case | A-6 ST CPL | 2027-09-05 | 2027-11-26 | 82 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | GC782-7 A-4 ST-DRL | 2027-11-26 | 2028-03-05 | 100 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | DRL | Early
Not Started | Early Case | GC782-7 A-4 CPL | 2028-03-05 | 2028-04-24 | 50 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | DVP | CPL | Early
Not Started | Early Case | TBD WSO pump & WL PH INTERV | 2028-03-10 | 2028-04-09 | 30 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Not Started | Early Case | MD14 (A13) P&A | 2028-04-24 | 2028-06-08 | 45 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | P&A | Early
Not Started | Early Case | Rig Maintenance Pull ODR | 2028-06-08 | 2028-06-22 | 14 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | X | RM | Early
Not Started | Early Case | TBD WSO pump & WL PH INTERV | 2029-01-04 | 2029-02-03 | 30 | GOM.Mad Dog | GOM.Mad Dog SPAR | GOM | WW | WWI | Early
Completed | Early Case | BWM Rig Maintenance | 2024-12-15 | 2025-01-17 | 33 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM (laying out BOP and picking up CWOR) | 2025-01-17 | 2025-01-24 | 7 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | BWM (CWOR deck test) | 2025-01-24 | 2025-02-20 | 27 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Completed | Early Case | MC778-2 (PDQ) INTERV | 2025-02-20 | 2025-03-26 | 18 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
Completed | Early Case | MC822-4 (PDQ) INTERV | 2025-03-26 | 2025-04-06 | 11 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
Completed | Early Case | MC822-7 (PDQ) INTERV | 2025-04-06 | 2025-04-18 | 15 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | WWP | Early
In Progress | Early Case | BWM (CWOR deck test) | 2025-04-18 | 2025-09-24 | 143 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Not Started | Early Case | MC778-8 PXA Open Water Work (PDQ) INTERV | 2025-09-24 | 2025-10-01 | 7 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | P&A | Early
Not Started | Early Case | SPi7/8 DRL (PDQ) | 2025-10-01 | 2026-01-30 | 121 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | DRL | Early
Not Started | Early Case | White Space | 2026-01-30 | 2026-03-01 | 30 | GOM.Region | GOM.PDQ | GOM | X | WS | Early
Not Started | Early Case | TAR | 2026-03-01 | 2026-05-19 | 79 | GOM.Thunder Horse | GOM.PDQ | GOM | OTH | TAR | Early
Not Started | Early Case | SPi7/8 CPL (PDQ) | 2026-05-19 | 2026-08-19 | 92 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | CPL | Early
Not Started | Early Case | Rig Maintenance | 2026-08-19 | 2026-09-18 | 30 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Not Started | Early Case | MC822-4 PXA (PDQ) INTERV | 2026-09-18 | 2026-11-27 | 70 | GOM.Thunder Horse | GOM.PDQ | GOM | WW | P&A | Early
Not Started | Early Case | White Space | 2026-11-27 | 2027-01-01 05:20 | 35 | GOM.Region | GOM.PDQ | GOM | X | WS | Early
Not Started | Early Case | SPi11/6 DRL (PDQ) | 2027-01-01 05:20 | 2027-05-11 05:20 | 130 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | DRL | Early
Not Started | Early Case | SPi11/6 CPL (PDQ) | 2027-05-11 05:20 | 2027-08-09 05:20 | 90 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | CPL | Early
Not Started | Early Case | Rig Maintenance | 2027-08-09 05:20 | 2027-09-08 05:20 | 30 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Not Started | Early Case | SPi4/5w DRL | 2027-09-08 05:20 | 2028-01-16 05:20 | 130 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | DRL | Early
Not Started | Early Case | SPi4/5w CPL | 2028-01-16 05:20 | 2028-04-15 05:20 | 90 | GOM.Thunder Horse | GOM.PDQ | GOM | DVI | CPL | Early
Not Started | Early Case | Rig Maintenance | 2028-04-15 05:20 | 2028-07-14 05:20 | 90 | GOM.Thunder Horse | GOM.PDQ | GOM | X | RM | Early
Not Started | Early Case | Rig Start up | 2025-10-01 | 2025-10-09 | 8 | GOM.Region | GOM.Q5000 | GOM | WW | RSU | Early
Not Started | Early Case | MC822-3 (RLWI) INTERV | 2025-10-09 | 2025-10-30 | 21 | GOM.Thunder Horse | GOM.Q5000 | GOM | WW | WWP | Early
Not Started | Early Case | Thunder Horse P45 C/O | 2025-10-30 | 2025-11-14 | 15 | GOM.Thunder Horse | GOM.Q5000 | GOM | WW | WWP | Early
Not Started | Early Case | Rig Start up | 2026-01-01 | 2026-01-09 | 8 | GOM.Region | GOM.TBD #02 | GOM | WW | RSU | Early
Not Started | Early Case | Restoration Place Holder INTERV | 2026-01-09 | 2026-02-13 | 35 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Early
Not Started | Early Case | White Space | 2026-02-13 | 2027-01-01 | 322 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Early
Not Started | Early Case | Restoration Place Holder INTERV | 2027-01-01 | 2027-06-30 | 180 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Early
Not Started | Early Case | White Space | 2027-06-30 | 2028-01-01 | 185 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Early
Not Started | Early Case | Restoration Place Holder INTERV | 2028-01-01 | 2028-06-29 | 180 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Early
Not Started | Early Case | White Space | 2028-06-29 | 2029-01-01 | 186 | GOM.Region | GOM.TBD #02 | GOM | X | WS | Early
Not Started | Early Case | Restoration Place Holder INTERV | 2029-01-01 | 2029-06-30 | 180 | GOM.Region | GOM.TBD #02 | GOM | WW | WWP | Early
Not Started | Early Case | Rig Start up | 2026-04-01 | 2026-05-06 | 35 | GOM.Region | GOM.TBD #07 | GOM | WW | RSU | Early
Not Started | Early Case | DC105 (MFXB75) DRL | 2026-05-06 | 2026-07-05 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | DRL | Early
Not Started | Early Case | DC105 (MFXB75) CPL | 2026-07-05 | 2026-08-24 | 50 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | CPL | Early
Not Started | Early Case | ATL DC152 DRL | 2026-08-24 | 2026-10-10 | 47 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Early
Not Started | Early Case | ATL DC152 CPL | 2026-10-10 | 2026-11-13 | 34 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | DC106 (MFXN54) DRL | 2026-11-13 | 2026-12-23 | 40 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | DRL | Early
Not Started | Early Case | DC106 (MFXN54) CPL | 2026-12-23 | 2027-01-27 | 35 | GOM.Atlantis | GOM.TBD #07 | GOM | MPI | CPL | Early
Not Started | Early Case | DC123 RE-CPL | 2027-01-27 | 2027-03-28 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | Isabela 1 (I-1) PA | 2027-03-28 | 2027-05-23 | 56 | GOM.Nakika | GOM.TBD #07 | GOM | WW | P&A | Early
Not Started | Early Case | NBr7 BWM | 2027-05-23 | 2027-05-25 | 2 | GOM.Thunder Horse | GOM.TBD #07 | GOM | X | RM | Early
Not Started | Early Case | NBr7 DRL | 2027-05-25 | 2027-09-10 | 108 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | DRL | Early
Not Started | Early Case | NBr7 CPL | 2027-09-10 | 2027-10-25 | 45 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | CPL | Early
Not Started | Early Case | Far South 2 Appraisal DRL | 2027-10-25 | 2028-02-02 | 100 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Early
Not Started | Early Case | ATL ST PH DRL #1 | 2028-02-02 | 2028-04-02 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Early
Not Started | Early Case | ATL ST PH CPL #1 | 2028-04-02 | 2028-05-02 | 30 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | ATL ST PH DRL #2 | 2028-05-02 | 2028-07-01 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Early
Not Started | Early Case | ATL ST PH CPL #2 | 2028-07-01 | 2028-07-31 | 30 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | NPi18 DRL | 2028-07-31 | 2028-11-13 | 105 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | DRL | Early
Not Started | Early Case | NPi18 CPL | 2028-11-13 | 2028-12-28 | 45 | GOM.Thunder Horse | GOM.TBD #07 | GOM | MPP | CPL | Early
Not Started | Early Case | MC775-3 (NPi13) PA | 2028-12-28 | 2029-01-27 | 30 | GOM.Thunder Horse | GOM.TBD #07 | GOM | WW | P&A | Early
Not Started | Early Case | APOLLO DRL | 2029-01-27 | 2029-04-27 | 90 | GOM.GOMX | GOM.TBD #07 | GOM | MPP | DRL | Early
Not Started | Early Case | ATL ST PH DRL #3 | 2029-04-27 | 2029-06-26 | 60 | GOM.Atlantis | GOM.TBD #07 | GOM | MPP | DRL | Early
Not Started | Early Case | ATL ST PH CPL #3 | 2029-06-26 | 2029-07-26 | 30 | GOM.Atlantis | GOM.TBD #07 | GOM | MPP | CPL | Early
Not Started | Early Case | ATL ST PH4 ST DRL | 2029-07-26 | 2029-09-12 | 48 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | DRL | Early
Not Started | Early Case | ATL ST PH4 ST CPL | 2029-09-12 | 2029-10-17 | 35 | GOM.Atlantis | GOM.TBD #07 | GOM | DVP | CPL | Early
Not Started | Early Case | Exploration PH6 DRL | 2029-10-17 | 2030-01-15 | 90 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Early
Not Started | Early Case | Exploration PH7 DRL | 2030-01-15 | 2030-04-15 | 90 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Early
Not Started | Early Case | Exploration PH8 DRL | 2030-04-15 | 2030-07-14 | 90 | GOM.GOMX | GOM.TBD #07 | GOM | EXP | DRL | Early